## Sheet3
Project ID | Project | Project Manager | Organization | Region | Plan Start | Plan Finish | OD | AD | BAC | Foreign | AC | ETC
A00130 | Establishment of Fatima Jinnah Institute of Dental Sciences, Jubilee Town, Lahore | Communication & Works Department, Punjab Information Technology Board (PITB) | Specialized Healthcare and Medical Education Department | North Single | 2013-04-01 | 2026-06-30 | 158 | 146 | 4480.577 | 0 | 3801.188 | 679.389 | APPROVED 12-08-2013
A00989 | Flood Protection of Sialkot against Aik, Bhed, and Palkhu Nullah | Irrigation | Irrigation | North Single | 2015-06-10 | 2026-06-30 | 132 | 120 | 4787.145 | 0 | 3643.68 | 1143.465 | APPROVED 12-06-2015
A01803 | Addition/alteration to Lahore High Court, Lahore | Provincial Buildings Division | Judiciary | North Single | 2014-07-01 | 2028-06-29 | 167 | 131 | 2000 | 0 | 1221.949 | 778.051 | APPROVED 01-07-2015
A01886 | Construction of Multan Metro Bus Project, Bus Depot and Command & Control Center (Pakage-9), Multan | MDA | Transport & Masstransit Department, GoPb | South Single | 2015-02-19 | 2025-06-30 | 124 | 124 | 2047.673 | 0 | 1942.673 | 105 | APPROVED 01-07-2015
A02194 | Energy Efficiency & Conservation Programme (PGDP, DLI-5) | Energy Department, Punjab Energy Efficiency & Conservation Agency | Energy Department | Punjab Based | 2020-12-18 | 2026-06-30 | 66 | 54 | 3615.016 | 0 | 3500 | 115.016 | APPROVED 07-09-2015
A02309 | Rehabilitation of Trimmu Sidhnai Link Canal | Irrigation | Government of Punjab | North Single | 2015-10-20 | 2025-07-31 | 117 | 116 | 2225.812 | 0 | 833.357 | 1392.455 | APPROVED 20-10-2015
A02607 | Land Acquisition for Jalalpur Irrigation Project | Irrigation | Irrigation | North Single | 2016-01-05 | 2025-07-31 | 114 | 113 | 3663.95 | 0 | 3662.95 | 1 | APPROVED 05-01-2016
A03293 | Enhanced HIV / AIDS Control Programme Punjab (3 Years) (Phase-II) | Directorate General Health Services Punjab, Health, Health & Population Department | Health & Population Department | Punjab Based | 2016-07-01 | 2026-06-30 | 119 | 107 | 3829.871 | 0 | 2976.339 | 853.532 | APPROVED 15-07-2016
A04013 | Punjab Intermediate Cities Improvement Investment Prgramme | LG&CD Department | Government of Punjab | North Single | 2016-07-01 | 2026-06-25 | 119 | 107 | 62280.9 | 49302.3 | 37361 | 24919.9 | APPROVED 05-05-2017
A04508 | Construction of Flood Bund along River Indus from Rakh Bagh Wala to Bait Wagwar Kot Mithan District Rajanpur RD 0-275 | Irrigation | Irrigation | South Single | 2016-12-13 | 2025-07-31 | 103 | 102 | 1645.936 | 0 | 946.304 | 699.632 | APPROVED 14-12-2016
A04518 | Construction of Dadhocha Dam | Government of The Punjab, Irrigation | Government of Punjab, Planning & Development Board, Punjab | North Single | 2017-07-01 | 2026-07-18 | 108 | 95 | 14454.256 | 0 | 9233.826 | 5220.43 | APPROVED 02-01-2018
A04523 | Construction of New Campus of Government Engineering Academy Punjab | Irrigation | Irrigation | North Single | 2016-04-04 | 2025-07-10 | 111 | 110 | 1365.7 | 0 | 856.7 | 509 | APPROVED 08-06-2016
A04707 | Punjab Tourism For Economic Growth Project (PTEGP) - World Bank Assisted | Planning & Development Board, Punjab | Planning & Development Board, Punjab | Punjab Based | 2017-10-10 | 2025-06-30 | 92 | 92 | 8525 | 7750 | 8000 | 525 | APPROVED 12-10-2017
A06350 | Southern Punjab Poverty Alleviation Project (SPPAP)-IFAD Assisted | Planning & Development Board, Punjab | Planning & Development Board, Punjab | Multiple Region | 2011-09-30 | 2028-03-31 | 198 | 165 | 25243.13 | 22967.38 | 20017.553 | 5225.577 | APPROVED 30-09-2011
A06822 | Upscaling of Green Pakistan Program | Forestry, Wildlife & Fisheries | Government of Punjab | Punjab Based | 2016-07-01 | 2028-06-30 | 143 | 107 | 13187.629 | 0 | 8287.629 | 4900 | APPROVED 04-07-2019
A06958 | Addition / Alteration to Lahore High Court, Bahawalpur, Multan & Rawalpindi Benches | Communication & Works Department | Judiciary | Multiple Region | 2017-07-01 | 2028-06-28 | 131 | 95 | 2375.255 | 0 | 1100 | 1275.255 | APPROVED 01-07-2017
A07189 | Upgradation and Environmental Improvement of Chungi No. 09 Disposal Station Multan. | WASA Multan | HUD&PHED | South Single | 2021-12-24 | 2027-06-30 | 66 | 42 | 3432.84 | 0 | 2630.625 | 802.215 | APPROVED 01-12-2019
A07434 | Extension and Rehabilitation of Qutab Drain | Irrigation | Irrigation | South Single | 2017-07-01 | 2025-07-31 | 96 | 95 | 3620.171 | 0 | 1902.329 | 1717.842 | APPROVED 02-01-2018
A07608 | Construction of Jalalpur Irrigation Project and its System | Irrigation | Irrigation | North Single | 2018-07-01 | 2026-06-29 | 95 | 83 | 32721.46 | 27972.47 | 21350.094 | 11371.366 | APPROVED 07-02-2018
A08295 | Ten Billion Tree Tsunami Programme (Phase-1) Up-scaling of Green Pakistan Programme (Revised) | Communication & Works Department, Fisheries, Forestry, Wildlife | Federal Fund, Government of Punjab | Punjab Based | 2016-07-01 | 2025-06-30 | 107 | 107 | 2945.3 | 0 | 1554.277 | 1391.023 | APPROVED 17-01-2017
A10125 | Channelization of Deg Nullah (Land Acquisition Punjab Component) | Irrigation | Irrigation | North Single | 2016-11-30 | 2025-07-31 | 104 | 103 | 3175.485 | 0 | 3174.485 | 1 | APPROVED 30-11-2016
A11463 | Establishment of Sports Complex Model Bazar China Scheme, Lahore (LDP). | LDA | HUD&PHED | North Single | 2017-07-02 | 2028-06-30 | 131 | 95 | 1261.466 | 0 | 923.976 | 337.49 | APPROVED 14-07-2017
A11468 | Establishment of Sports Complex Kahna Lahore (LDP). | LDA | HUD&PHED | North Single | 2017-07-01 | 2027-06-30 | 119 | 95 | 2295.839 | 0 | 985.776 | 1310.063 | APPROVED 14-07-2017
A11979 | Construction of Building of Women University, Sialkot on acquired piece of land at Sialkot | Higher Education Department | Higher Education Department | North Single | 2017-02-10 | 2026-06-30 | 112 | 100 | 2946.888 | 0 | 2018.291 | 928.597 | APPROVED 02-10-2017
A14231 | Multi Sectoral Nutrition Strategy for WASH Including Water Supply, Sanitation, Hygiene, Waste Water | Water Supply & Sanitation | HUD&PHED | Punjab Based | 2017-07-01 | 2026-06-30 | 107 | 95 | 1108.063 | 0 | 762.536 | 345.527 | APPROVED 01-07-2017
A16411 | Repair / Rehabilitation of Road from Sillanwali to Chak No. 58/janubi via 119 More, 126/SB, Length 39.80 Km, District Sargodha | Communication & Works Department | Government of Punjab | North Single | 2015-07-01 | 2028-06-28 | 155 | 119 | 1328.735 | 0 | 1056.569 | 272.166 | APPROVED 01-07-2015
A16475 | Widening/Improvement of road from faisal Chowk to Darya Khan Road | Communication & Works Department | Communication & Works Department | North Single | 2015-07-01 | 2028-06-30 | 155 | 119 | 1696.211 | 0 | 1690.211 | 6 | APPROVED 31-07-2017
A16486 | Construction of Dual Carriage way from Faisalabad Dry Port to Sahianwala Via Chak Jhumra, L= 18.90 km District Faisalabad | Communication & Works Department | Government of Punjab | North Single | 2016-07-01 | 2026-06-30 | 119 | 107 | 1247.713 | 0 | 1005.582 | 242.131 | APPROVED 01-07-2017
A16847 | Construction of Additional Ring Road Bahawalpur Railway Station to Bino Hospital via Bindra Pully Dewan pully Sadar pully Kali pully Bahawalpur. | Communication & Works Department | Communication & Works Department | South Single | 2015-07-01 | 2028-06-30 | 155 | 119 | 1161.055 | 0 | 1160.055 | 1 | APPROVED 31-07-2017
A16917 | Construction of bye pass from Royal Hotel (N-5) to Sarwar Chowk Via Adda Mai Wali Masjid, Length 13.70 Km, District Sahiwal | Communication & Works Department | Government of Punjab | North Single | 2017-07-01 | 2026-06-28 | 107 | 95 | 1988.47 | 0 | 1987.47 | 1 | APPROVED 13-11-2017
A17475 | Widening / improvement of single road from Noorpur Thal to Jhang Road, length=55.00 Km via Daduwala, Shah Hussain, Tehsil Noorpur Thal, District Khushab | Communication & Works Department | Communication & Works Department | North Single | 2017-07-01 | 2028-06-30 | 131 | 95 | 1343.848 | 0 | 706.112 | 637.736 | APPROVED 26-12-2017
A22167 | Project Readiness Financing Facility for Punjab Water Resources Management | Industries, Commerce & Investment | Irrigation | Punjab Based | 2020-02-21 | 2025-07-30 | 65 | 64 | 1276.324 | 1231.653 | 650.992 | 625.332 | APPROVED 01-08-2019
A24312 | Addition / Alteration & Improvement Works in Government Colonies Lahore | Communication & Works Department | S&GAD | North Single | 2023-07-01 | 2026-06-30 | 35 | 23 | 2295 | 0 | 2119.673 | 175.327 | APPROVED 01-07-2022
A24313 | Addition / Alteration & Improvement Works in GORs, Lahore | Communication & Works Department | S&GAD | North Single | 2023-07-01 | 2026-06-30 | 35 | 23 | 3400 | 0 | 3059.206 | 340.794 | APPROVED 01-07-2022
A24316 | Renewable Energy Development Sector Investment Programme (REDSIP) | Energy Department | Energy Department | North Single | 2013-11-07 | 2026-06-30 | 151 | 139 | 12861 | 0 | 11478.808 | 1382.192 | APPROVED 04-03-2014
A24328 | Addition / Alteration & Improvement Works in Office Buildings, Punjab Civil Secretariat, Lahore | Communication & Works Department | S&GAD | North Single | 2023-07-01 | 2026-06-30 | 35 | 23 | 1108.729 | 0 | 918.65 | 190.079 | APPROVED 01-07-2022
A24627 | PPIC3 Rawalpindi | Communication & Works Department, Punjab Information Technology Board (PITB), Punjab Safe Cities Authority (PSCA) | Police Department | North Single | 2017-04-01 | 2025-12-30 | 104 | 98 | 5251.294 | 0 | 3537.781 | 1713.513 | APPROVED 06-01-2017
A24630 | PPIC3 Faisalabad | Communication & Works Department, Punjab Information Technology Board (PITB), Punjab Safe Cities Authority (PSCA) | Police Department | North Single | 2017-01-06 | 2025-12-30 | 107 | 101 | 4215.603 | 0 | 3375.266 | 840.337 | APPROVED 06-01-2017
A24631 | PPIC3 Gujranwala | Communication & Works Department, Punjab Information Technology Board (PITB), Punjab Safe Cities Authority (PSCA) | Police Department | North Single | 2017-01-06 | 2025-12-30 | 107 | 101 | 4182.549 | 0 | 3009.552 | 1172.997 | APPROVED 06-01-2017
A25292 | Lahore Water and Waste Water Management Project - Construction of Surface Water Treatment Plant at BRBD Canal Lahore. | WASA Lahore | HUD&PHED | North Single | 2018-09-15 | 2028-06-30 | 117 | 81 | 21045.71 | 21045.71 | 119.345 | 20926.365 | APPROVED 01-03-2019
A25616 | Punjab Rozgar | Punjab Small Industries Corporation (PSIC) | Industries, Commerce & Investment | Punjab Based | 2020-04-01 | 2026-06-29 | 74 | 62 | 10000 | 0 | 4790.246 | 5209.754 | APPROVED 30-09-2020
A26186 | Rehabilitation and Modernization of Islam Barrage | Irrigation | Irrigation | South Single | 2019-12-31 | 2025-12-31 | 72 | 65 | 2993.18 | 2104.72 | 4801.266 | -1808.086 | APPROVED 06-08-2019
A26215 | Establishment of 200 Bedded Mother & Child Hospital in District Layyah | Infrastructure Development Authority Punjab (IDAP) | Federal Fund, Health & Population Department | South Single | 2021-03-15 | 2025-07-14 | 51 | 51 | 5944.228 | 0 | 5444.228 | 500 | APPROVED 28-09-2020
A26216 | Establishment of 300-Bedded DHQ Hospital Mianwali (New Block) | Infrastructure Development Authority Punjab (IDAP) | Health & Population Department | North Single | 2019-07-30 | 2025-06-30 | 71 | 71 | 7997.45 | 0 | 7996.45 | 1 | APPROVED 17-06-2019
A27463 | Construction of MPA Hostel Lahore Phase II | Communication & Works Department | Provincial Assembly | North Single | 2019-07-01 | 2027-06-30 | 95 | 71 | 6296.749 | 0 | 2480.684 | 3816.065 | APPROVED 06-01-2020
A28143 | Establishment of Tertiary Care Hospital (Nishtar -II), Multan | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | South Single | 2019-07-01 | 2026-06-30 | 83 | 71 | 13368.643 | 0 | 9992.602 | 3376.041 | APPROVED 20-08-2019
A28430 | Construction of four(04) sewage treatment plants and required sewerage lines under Phase-I(Rawal Lake and its surroundings including the Catchment area. 36% GoPb share) | WASA Rawalpindi | HUD&PHED | North Single | 2019-03-01 | 2026-06-30 | 87 | 75 | 5244.7 | 0 | 0 | 5244.7 | APPROVED 16-01-2019
A28453 | Establishment of Teaching Hospital (Sheikh Zayed-II), Rahim Yar Khan | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | South Single | 2019-07-01 | 2026-06-30 | 83 | 71 | 7066.9 | 0 | 3440 | 3626.9 | APPROVED 18-12-2020
A28611 | Construction of Eastern Wastewater Treatment Plant 33 MGD of Faisalabad City Phase-I (DANIDA Assisted). | WASA Faisalabad | HUD&PHED | North Single | 2020-07-28 | 2030-08-31 | 121 | 59 | 56036.79 | 53221.26 | 366.291 | 55670.499 | APPROVED 22-10-2019
A28867 | Dualization of Muzaffargarh Road (Jauharabad – Chowk Girote), Length 25 Km, District Khushab | Communication & Works Department | Communication & Works Department | North Single | 2019-07-01 | 2028-06-30 | 107 | 71 | 3460.093 | 0 | 2390.602 | 1069.491 | APPROVED 15-10-2019
A28964 | Construction of building of Muhammad Nawaz Sharif University of Engineering & Technology, Multan | Communication & Works Department, Higher Education Department | Higher Education Department | South Single | 2020-07-01 | 2026-06-30 | 71 | 59 | 1018.062 | 0 | 917.774 | 100.288 | APPROVED 24-04-2020
A28967 | Construction of building of Ghazi University, D.G.Khan | Ghazi University | Higher Education Department | South Single | 2019-07-01 | 2026-06-30 | 83 | 71 | 1349.257 | 0 | 854.353 | 494.904 | APPROVED 24-12-2019
A29191 | Establishment of Khawaja Fareed University of Engineering and Information Technology RY Khan (Phase-II) | KFUEIT, RYK | Higher Education Department | South Single | 2019-07-01 | 2026-06-30 | 83 | 71 | 2017.548 | 0 | 2016.544 | 1.004 | APPROVED 17-12-2019
A29597 | Heritage and Urban Regeneration in Lahore Fort (AFD Funded) | LG&CD Department | LG&CD Department | North Single | 2022-07-07 | 2027-07-06 | 59 | 35 | 4036.59 | 3662.68 | 540 | 3496.59 | APPROVED 09-08-2021
A29674 | Establishment of University of Child Health Sciences at Lahore | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | North Single | 2021-07-01 | 2026-06-29 | 59 | 47 | 4265.753 | 0 | 1500 | 2765.753 | APPROVED 15-02-2022
A29687 | Punjab Agriculture Food and Drug Authority | Infrastructure Development Authority Punjab (IDAP) | Home Department | North Single | 2018-07-01 | 2025-06-30 | 83 | 83 | 15610.27 | 0 | 15610.265 | 0.005 | APPROVED 23-06-2017
A29722 | Program to Uplift Water Supply & Sanitation Infrastructure in Underdeveloped Areas of Punjab. | Water Supply & Sanitation | HUD&PHED | Punjab Based | 2019-07-01 | 2026-06-30 | 83 | 71 | 3608.639 | 0 | 3206.036 | 402.603 | APPROVED 10-02-2020
A29732 | Replacement of outlived water supply lines and tube wells in Multan | WASA Multan | HUD&PHED | South Single | 2019-07-01 | 2025-06-28 | 71 | 71 | 1094.85 | 0 | 1030 | 64.85 | APPROVED 28-01-2020
A29781 | Construction of Punjab Judicial Academy at Kala Shah Kaku Lahore (Phase-II) | Communication & Works Department | Law & Parliamentary Affairs | North Single | 2019-07-01 | 2025-06-30 | 71 | 71 | 3323.774 | 0 | 1847.982 | 1475.792 | APPROVED 10-03-2020
A29792 | Establishment of University of Chakwal | Higher Education Department | Higher Education Department | North Single | 2020-07-01 | 2026-06-30 | 71 | 59 | 1543.994 | 0 | 1257.148 | 286.846 | APPROVED 11-12-2020
A29803 | Project Readiness Financing (PRF) for Punjab Provincial Projects- Punjab Intermediate Cities Improvement Investment Program (PHASE-II) | LG&CD Department | LG&CD Department | Multiple Region | 2020-11-30 | 2025-06-28 | 54 | 55 | 4625.52 | 3854.6 | 2531 | 2094.52 | APPROVED 30-10-2019
A29829 | Punjab Cities Programme, TA Component | LG&CD Department | World Bank | Multiple Region | 2019-07-01 | 2026-03-31 | 80 | 71 | 3058 | 3058 | 2120 | 938 | APPROVED 18-11-2019
A29843 | Re-construction of Old P&D Building, Lahore | S&GAD | S&GAD | North Single | 2023-07-01 | 2026-06-30 | 35 | 23 | 5867.61 | 0 | 5000 | 867.61 | APPROVED 06-06-2023
A29938 | Establishment of 200 Bedded Mother & Child Hospital in District Rajanpur | Infrastructure Development Authority Punjab (IDAP) | Federal Fund, Health & Population Department | South Single | 2021-03-15 | 2024-03-14 | 35 | 51 | 9028.75 | 0 | 3867.03 | 5161.72 | APPROVED 11-01-2021
A30164 | Dualization of Sialkot Pasrur Road, District Sialkot | Communication & Works Department | Communication & Works Department, Government of Punjab | North Single | 2019-09-02 | 2028-06-29 | 105 | 69 | 6494.731 | 0 | 6156.628 | 338.103 | APPROVED 15-10-2019
A30169 | Construction of Flyover at Nadirabad Phatak to Industrial Estate , Multan. | Communication & Works Department | Roads | South Single | 2020-02-04 | 2028-06-30 | 100 | 64 | 5377.162 | 0 | 4114.315 | 1262.847 | APPROVED 05-03-2020
A30179 | Dualization of Lodhran Kheror Pacca, Malsi Vehari Road District Lodhran (Phase-II) Remaining 20 Km | Communication & Works Department | Communication & Works Department, Government of Punjab | South Single | 2019-09-02 | 2028-06-29 | 105 | 69 | 4242.283 | 0 | 1607.819 | 2634.464 | APPROVED 25-10-2019
A30284 | Rehabilitation / Improvement of Sewerage System, District Jhang (Phase-I) | Water Supply & Sanitation | HUD&PHED | North Single | 2019-05-31 | 2026-06-30 | 84 | 72 | 1381.446 | 0 | 813.38 | 568.066 | APPROVED 11-12-2019
A30442 | Dualization / Improvement of Multan Mattital Road (length 21 Kms) District Multan | Communication & Works Department | Communication & Works Department, Government of Punjab | South Single | 2019-09-02 | 2028-06-30 | 105 | 69 | 2618.161 | 0 | 2166.296 | 451.865 | APPROVED 15-10-2019
A30587 | Establishment of Project Management Unit(PMU):Revamping work of DHQ/THQ Hospitals in the Punjab | Health & Population Department | Health & Population Department | Punjab Based | 2019-07-17 | 2025-06-30 | 71 | 71 | 1631.132 | 0 | 1449.267 | 181.865 | APPROVED 17-07-2019
A31539 | Construction of Residences for Judicial Officers at Faisalabad Headquarter | Communication & Works Department | Judiciary | North Single | 2020-07-01 | 2026-06-29 | 71 | 59 | 1379.723 | 0 | 1320.084 | 59.639 | APPROVED 09-04-2020
A31658 | Construction of District Jail, Nankana Sahib (NRP) | Communication & Works Department | Home Department | North Single | 2021-03-01 | 2025-06-29 | 51 | 51 | 2238.17 | 0 | 1455.731 | 782.439 | APPROVED 28-07-2021
A32435 | Transforming the Indus Basin with Climate Resilient Agriculture and Climate-Smart Water Management (2022-23 to 2027-28) | Agriculture Department | Agriculture Department | South Single | 2020-07-01 | 2028-06-29 | 95 | 59 | 1392 | 0 | 626.4 | 765.6 | APPROVED 26-10-2021
A32587 | Design and Construction of Net Zero Energy Building (ACEIP , DLI-8) | Energy Department | Energy Department | North Single | 2020-07-01 | 2027-06-30 | 83 | 59 | 5781.95 | 0 | 2085 | 3696.95 | APPROVED 25-01-2021
A32737 | Punjab Human Capital Investment Project (PHCIP) | Primary and Secondary Healthcare Department, Punjab Social Protection Authority, School Education Department | Planning & Development Board, Punjab | Multiple Region | 2020-04-30 | 2026-06-30 | 74 | 62 | 41664 | 41664 | 31811 | 9853 | APPROVED 18-05-2020
A32907 | Baba Gurunanak University Nankana Sahib (Phase-I) | Communication & Works Department, Higher Education Department | Government of Punjab, Higher Education Department | North Single | 2021-02-23 | 2026-06-30 | 64 | 52 | 2299.962 | 0 | 1741.156 | 558.806 | APPROVED 23-02-2021
A32962 | Enhanced Air Quality Monitoring System In Punjab (DLI-2, PGDP) | Environment Protection & Climate Change Department | Environment Protection & Climate Change Department | Punjab Based | 2021-07-01 | 2025-06-30 | 47 | 47 | 5205.3 | 0 | 3398.5 | 1806.8 | APPROVED 14-10-2021
A33405 | Establishment of Mother & Child Block, Teaching Hospital, DG Khan | Communication & Works Department, DG Khan Medical College | Specialized Healthcare and Medical Education Department | South Single | 2020-07-01 | 2026-06-30 | 71 | 59 | 4463.757 | 0 | 1081.935 | 3381.822 | APPROVED 11-12-2020
A33884 | Enhanced Water Quality Monitoring System In Punjab (DLI-2, PGDP) | Environment Protection & Climate Change Department | Environment Protection & Climate Change Department | Punjab Based | 2020-07-01 | 2024-06-30 | 47 | 59 | 2972.72 | 0 | 1144.9 | 1827.82 | APPROVED 28-10-2021
A34010 | Extension of Colony Protection Bund of Marala Barrage and Realignment of Tunnelwah Nullah in Sialkot District | Irrigation | Irrigation | North Single | 2020-07-01 | 2026-06-30 | 71 | 59 | 3162.289 | 0 | 708 | 2454.289 | APPROVED 29-07-2024
A34257 | Establishment of 200 Bedded Mother & Child Hospital in District Bahawalnagar | Infrastructure Development Authority Punjab (IDAP) | Federal Fund, Health & Population Department | South Single | 2021-03-01 | 2025-06-30 | 51 | 51 | 6385.33 | 0 | 3375.335 | 3009.995 | APPROVED 11-03-2021
A34384 | Construction of South Punjab Secretariat & GOR At Bahawalpur and Multan | Infrastructure Development Authority Punjab (IDAP) | S&GAD SPb | South Single | 2021-02-11 | 2025-06-30 | 52 | 52 | 7407.027 | 0 | 3522.374 | 3884.653 | APPROVED 18-12-2020
A34413 | Induction of Eco-Friendly Buses in Cities of Punjab (DLI-6 PGDP) | Punjab Transport Company (PTC), GoPb, Transport & Masstransit Department, GoPb | Transport & Masstransit Department, GoPb | North Single | 2023-11-03 | 2026-05-31 | 30 | 19 | 4582.589 | 0 | 4151.78 | 430.809 | APPROVED 03-12-2021
A34447 | Extension of District Courts Complex Multan | Communication & Works Department, Infrastructure Development Authority Punjab (IDAP) | Judiciary | South Single | 2022-02-10 | 2027-06-30 | 64 | 40 | 5624.016 | 0 | 2448.452 | 3175.564 | APPROVED 12-05-2022
A34471 | Provision of Infrastructural, Academic and Operational Facilities to the Punjab University of Technology, Rasul, M.B.Din | Communication & Works Department | Commerce & Investment | North Single | 2021-07-01 | 2026-06-29 | 59 | 47 | 7525.541 | 0 | 5049.411 | 2476.13 | APPROVED 23-09-2021
A34473 | Upgradation of DHQ Hospital District Hafizabad | Health & Population Department | Federal Fund, Health & Population Department | North Single | 2021-03-24 | 2024-06-30 | 39 | 51 | 9795.184 | 0 | 6013.839 | 3781.345 | APPROVED 01-04-2021
A34987 | Construction of Population Welfare House, Punjab | Health & Population Department | Health & Population Department | Punjab Based | 2021-07-01 | 2026-06-30 | 59 | 47 | 1172.074 | 0 | 1071.566 | 100.508 | APPROVED 23-02-2022
A35145 | Construction of Gated Head Regulators from RD:205+000 to 283+000 of BRBD Link Canal | Irrigation | Irrigation | North Single | 2021-07-01 | 2025-08-13 | 49 | 47 | 1125.87 | 0 | 716.126 | 409.744 | APPROVED 03-09-2021
A35450 | Rehabilitation / Renovation Existing Office Buildings and Construction of New Office Block of Commissioner Office, Lahore | Communication & Works Department | S&GAD | North Single | 2021-07-01 | 2026-06-30 | 59 | 47 | 1253 | 0 | 1250 | 3 | APPROVED 10-08-2021
A35544 | Construction of Building at University of Chakwal (City Campus) | Higher Education Department | Higher Education Department | North Single | 2021-10-21 | 2026-06-30 | 56 | 44 | 1582.893 | 0 | 1432.043 | 150.85 | APPROVED 21-10-2021
A35568 | Koh-E-Suleman Improvement Project (KSIP) | Planning & Development Board, Punjab | Planning & Development Board, Punjab | South Single | 2021-07-01 | 2026-06-30 | 59 | 47 | 5712 | 0 | 3573.033 | 2138.967 | APPROVED 15-07-2021
A35606 | Establishment of Public Financial Management Unit (PFMU), Finance Department & Program Support Unit (PSU) Planning & Development Board under Punjab Resource Improvement and Digital Effectiveness (PRIDE)-TA Component | Finance Department, Planning & Development Board, Punjab | Planning & Development Board, Punjab | Punjab Based | 2021-07-01 | 2025-06-30 | 47 | 47 | 4968.6 | 4968.6 | 253.772 | 4714.828 | APPROVED 19-05-2021
A35742 | Rehabilitation of Road from Qila Dedar Singh to Sheikhupra Road Ghuman Wala, Gujranwala. | GDA | HUD&PHED | North Single | 2021-10-07 | 2028-06-30 | 80 | 44 | 1431.913 | 0 | 850.334 | 581.579 | APPROVED 07-10-2021
A35995 | Construction of Sorra Dam | Irrigation | Irrigation | South Single | 2021-07-01 | 2026-06-30 | 59 | 47 | 8151.58 | 0 | 1392 | 6759.58 | APPROVED 14-09-2021
A36137 | Establishment of University of Applied Engineering and Emerging Technologies (UAEET), Sialkot | Infrastructure Development Authority Punjab (IDAP) | Higher Education Department | North Single | 2021-09-08 | 2027-06-30 | 69 | 45 | 17685.703 | 0 | 3169.785 | 14515.918 | APPROVED 03-11-2022
A36262 | Punjab Rural Sustainable Water Supply and Sanitation Project | LG&CD Department | LG&CD Department | Punjab Based | 2021-07-01 | 2028-06-30 | 83 | 47 | 96202 | 76962 | 39125 | 57077 | APPROVED 12-04-2021
A36267 | Establishment of University of Gujranwala | Higher Education Department | Higher Education Department | North Single | 2023-08-22 | 2026-06-30 | 34 | 22 | 5299.714 | 0 | 1335.591 | 3964.123 | APPROVED 22-08-2023
A36275 | Establishment of University of Hafizabad | Communication & Works Department, University of Hafizabad | Higher Education Department | North Single | 2021-07-01 | 2026-06-30 | 59 | 47 | 1204.863 | 0 | 917.704 | 287.159 | APPROVED 21-10-2021
A36391 | Establishment of Emergency and OPD Block Teaching Hospital, DG Khan | Communication & Works Department, DG Khan Medical College | Specialized Healthcare and Medical Education Department | South Single | 2021-07-01 | 2026-06-29 | 59 | 47 | 4035.184 | 0 | 1111.57 | 2923.614 | APPROVED 17-09-2021
U36473 | Chaubara Branch Canal Construction Project - Greater Thal Canal (Phase-II) | Irrigation | Irrigation | Multiple Region | 2021-07-01 | 2027-06-30 | 71 | 47 | 1000 | 0 | 0 | 1000 | UN-APPROVED
A36494 | Establishment of 200 Bedded Mother & Child Hospital at Ghalla Godam, Multan | Communication & Works Department, Nishtar Medical University & Allied Hospital, Multan | Specialized Healthcare and Medical Education Department | South Single | 2021-04-07 | 2026-06-30 | 62 | 50 | 8116.778 | 0 | 2931.749 | 5185.029 | APPROVED 07-04-2021
A36631 | Rehabilitation / Construction of office/residential complex for the newly created Zones / Circles / Divisions/ Sub divisions | Irrigation | Irrigation | Multiple Region | 2021-07-01 | 2025-07-30 | 48 | 47 | 1100.066 | 0 | 160 | 940.066 | APPROVED 02-11-2021
U37177 | Construction of Bachelor Hostel/ Residences for Officers / Officials of P&D Board at Lahore | Communication & Works Department | Planning & Development Board, Punjab | North Single | 2021-07-01 | 2025-06-30 | 47 | 47 | 1836 | 0 | 0 | 1836 | UN-APPROVED
A37208 | Implementation of Universal Health Coverage under Health Insurance Program in Punjab | Punjab Health Initiative Management Company (PHIMC), Specialized Healthcare and Medical Education Department | Specialized Healthcare and Medical Education Department | Punjab Based | 2021-07-01 | 2026-06-30 | 59 | 47 | 332845 | 0 | 200499 | 132346 | APPROVED 22-09-2021
A37327 | Land Acquisition & Utility Shifting for Dualization of Faisalabad - Chiniot - Sargodha Road (Length =67 Km) - Under PPP Mode | Roads | Communication & Works Department | North Single | 2021-05-10 | 2026-06-30 | 61 | 49 | 3494.391 | 0 | 3127.247 | 367.144 | APPROVED 10-05-2021
A37431 | New Dhar Jawa Water Supply Scheme with new tourist spot IMP. Of Dhirkot Spring Water Supply Scheme Kotli Sattian & Augmentation of Water Supply / Drainage / Sewerage System at kahota Rawalpindi | Water Supply & Sanitation | HUD&PHED | North Single | 2021-01-07 | 2026-06-30 | 65 | 53 | 1070.527 | 0 | 832.203 | 238.324 | APPROVED 29-03-2022
A37474 | Improving Workforce Readiness in Punjab Project (Cost: FEC $100m, Local $10m) | Skill Development & Entrepreneurship Department | Skill Development & Entrepreneurship Department | Punjab Based | 2023-01-13 | 2028-12-29 | 71 | 29 | 23982 | 21896 | 6510.312 | 17471.688 | APPROVED 21-10-2022
A37690 | City Uplift Package Minchinabad (Sewerage, Drainage, Water Supply, Street Lights, Road) Tehsil Minchanabad City, District Bahawalnagar | Water Supply & Sanitation | HUD&PHED | South Single | 2021-01-07 | 2026-06-30 | 65 | 53 | 1017.838 | 0 | 599.47 | 418.368 | APPROVED 07-10-2021
A37944 | Comprehensive Sewerage, Drainage and water supply system in Gujrat City. | Water Supply & Sanitation | HUD&PHED | North Single | 2021-01-07 | 2026-06-30 | 65 | 53 | 1436.64 | 0 | 1158.504 | 278.136 | APPROVED 20-10-2021
A38258 | Revamping / Comprehensive Sewerage & Drainage I/C Tuff Tile And PCC Schemes for Mianwali City District Mianwali | Water Supply & Sanitation | HUD&PHED | North Single | 2021-01-07 | 2026-06-30 | 65 | 53 | 1076.786 | 0 | 1066.786 | 10 | APPROVED 24-09-2021
A38912 | Dualization / Improvement of road from MDA to Lodhi Colony via Pull Braran District Multan | Communication & Works Department | Government of Punjab | South Single | 2021-07-01 | 2028-06-30 | 83 | 47 | 1083.075 | 0 | 1071.865 | 11.21 | APPROVED 12-01-2022
A39076 | Construction of Under Pass at Katchehri-Rasulnagar Road Railway Crossing City Sheikhupura. | Communication & Works Department | Government of Punjab | North Single | 2021-07-01 | 2026-06-30 | 59 | 47 | 1390.71 | 0 | 1382.208 | 8.502 | APPROVED 12-01-2022
A39199 | Construction of Flyover at 47 Pull Tehsil & District Sargodha | Communication & Works Department | Government of Punjab | North Single | 2021-07-01 | 2027-06-29 | 71 | 47 | 2227.344 | 0 | 2226.344 | 1 | APPROVED 01-10-2021
A39577 | Construction of Byepass from Dhounkal More to Sohdra Wazirabad (Length= 8.10 km) Tehsil Wazirabad District Gujranwala (Punjab Roads & Bridges) | Communication & Works Department | Government of Punjab | North Single | 2021-07-01 | 2028-06-30 | 83 | 47 | 1393.554 | 0 | 593.423 | 800.131 | APPROVED 22-10-2021
A39634 | Dualization of road from Shadiwal to Chak Gillan District Gujrat | Communication & Works Department | Government of Punjab | North Single | 2021-07-01 | 2026-06-30 | 59 | 47 | 2138.631 | 0 | 2130.773 | 7.858 | APPROVED 07-09-2021
A39636 | Construction of Service More Flyover to connect with Industrial Area-II Gujrat link road in District Gujrat | Communication & Works Department | Government of Punjab | North Single | 2021-07-01 | 2028-06-30 | 83 | 47 | 2463.582 | 0 | 1805.6 | 657.982 | APPROVED 16-09-2021
A39646 | Construction of Flyover at Rajjar Railway Crossing Sarai Alamgir District Gujrat | Communication & Works Department | Government of Punjab | North Single | 2021-07-01 | 2028-06-30 | 83 | 47 | 1278.308 | 0 | 888.201 | 390.107 | APPROVED 05-10-2021
A39808 | Widening and Carpeting of metal road from Kotla Musa Khan to Kachi Mor and Flyover at Firdous Cinema Phatak Tehsil Ahmedpur East District Bahawalpur | Communication & Works Department | Government of Punjab | South Single | 2021-07-01 | 2028-06-30 | 83 | 47 | 1011.501 | 0 | 866.975 | 144.526 | APPROVED 04-11-2021
A40198 | Widening / Improvement of Khanewal road from Eid Gah chowk to Chowk Kumharan via Rasheedabad, Multan. | MDA | HUD&PHED | South Single | 2021-11-26 | 2028-06-30 | 79 | 43 | 1565.954 | 0 | 1438.511 | 127.443 | APPROVED 26-10-2021
A40989 | Umbrella PC-I for provision of land Acquisition / Compensation of structure and PST pertaining to PSDP funded schemes. | Communication & Works Department | Government of Punjab | South Single | 2021-07-01 | 2026-06-30 | 59 | 47 | 9816.476 | 0 | 7011.649 | 2804.827 | APPROVED 22-10-2021
A42996 | Program for Quality Seed Production and Dissemination (2021-22 to 2025-26) | Agriculture Department | Agriculture Department | Punjab Based | 2021-07-01 | 2026-06-29 | 59 | 47 | 1994.09 | 0 | 1480.3 | 513.79 | APPROVED 01-09-2021
U43149 | Chief Minister Priority Program | Planning & Development Board, Punjab | Planning & Development Board, Punjab | Punjab Based | 2022-07-01 | 2026-06-30 | 47 | 35 | 8000 | 0 | 0 | 8000 | UN-APPROVED
U43151 | VGF and Land Acquisition for Development Projects. | Planning & Development Board, Punjab | Planning & Development Board, Punjab | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 1000 | 0 | 0 | 1000 | UN-APPROVED
A43417 | Punjab Urban Land Systems Enhancements (PULSE) | BOR, Punjab Land Records Authority (PLRA) | World Bank | Punjab Based | 2022-07-01 | 2027-06-30 | 59 | 35 | 26440.704 | 26440.704 | 1479.67 | 24961.034 | APPROVED 23-12-2021
A44394 | Construction of Bachelor accommodation and Judicial Rest House at Dharampura, District Lahore | Communication & Works Department | Judiciary | North Single | 2022-07-01 | 2026-06-29 | 47 | 35 | 3687 | 0 | 3452.96 | 234.04 | APPROVED 04-10-2022
A44463 | Construction of Judicial Complex (Courts Block) at District Headquarter Muzaffargarh | Communication & Works Department | Judiciary | South Single | 2022-07-01 | 2026-06-29 | 47 | 35 | 2135.893 | 0 | 1225.605 | 910.288 | APPROVED 17-05-2023
A44477 | Construction of Judicial Complex at District Headquarter, Chiniot | Communication & Works Department | Judiciary | North Single | 2022-07-01 | 2026-06-29 | 47 | 35 | 2211 | 0 | 2008.686 | 202.314 | APPROVED 31-05-2022
A44478 | Construction of Court Complex at Depalpur, District Okara | Communication & Works Department | Judiciary | North Single | 2022-07-01 | 2026-06-29 | 47 | 35 | 1636.571 | 0 | 1524.571 | 112 | APPROVED 17-01-2023
A44493 | Strengthening of Punjab Tianjin University of Technology (PTUT), Lahore | Communication & Works Department, Punjab Tianjin University of Technology (PTUT) | Industries, Commerce & Investment | North Single | 2022-07-01 | 2026-06-29 | 47 | 35 | 6281.649 | 0 | 293.958 | 5987.691 | APPROVED 08-11-2022
A44502 | Construction of Judicial Complex at Ferozewala, District Sheikhupura | Communication & Works Department | Judiciary | North Single | 2022-07-01 | 2026-06-29 | 47 | 35 | 1676.66 | 0 | 1443.18 | 233.48 | APPROVED 23-09-2022
A44513 | Construction of New Administration Block at Lahore High Court, Multan Bench, Multan | Communication & Works Department | Judiciary | South Single | 2022-07-01 | 2026-06-29 | 47 | 35 | 2080.25 | 0 | 1068.468 | 1011.782 | APPROVED 07-01-2023
A44516 | Construction of Bridge and Approach Road to Parking at Lahore High Court, Rawalpindi Bench, Rawalpindi | Roads | Judiciary | North Single | 2022-07-01 | 2027-06-29 | 59 | 35 | 1322.39 | 0 | 675 | 647.39 | APPROVED 13-09-2022
A45051 | Construction of Dual Carriageway from Bosan Road (saidanwala Chowk) to Head Muhammadwala , Length =11.68 Km, Distrcit Multan | Communication & Works Department | Communication & Works Department | South Single | 2022-02-23 | 2028-06-30 | 76 | 40 | 1612.528 | 0 | 1433.961 | 178.567 | APPROVED 23-02-2022
A45110 | Construction of River Training Works for protection of LMB Qadirabad Barrage | Irrigation | Irrigation | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 1399.158 | 0 | 125 | 1274.158 | APPROVED 20-09-2024
A45184 | Establishment of Mir Chakar Khan Rind University of Technology, Dera Ghazi Khan | Communication & Works Department, Industries, Commerce & Investment | Industries, Commerce & Investment | South Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 4639.225 | 0 | 273 | 4366.225 | APPROVED 08-11-2022
A45331 | Punjab Resilient and Inclusive Agriculture Transformation (PRIAT) (2022-23 to 2026-27) | Agriculture Department | Agriculture Department, Government of Punjab | Punjab Based | 2022-07-01 | 2027-06-30 | 59 | 35 | 54935.56 | 45863.56 | 37250.317 | 17685.243 | APPROVED 18-11-2021
A45369 | Construction Of Green Building for EMC, EPD and Allied New Entities Established Under PGDP (DLI-2, PGDP) | Infrastructure Development Authority Punjab (IDAP) | Environment Protection & Climate Change Department | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 3723.93 | 0 | 2378 | 1345.93 | APPROVED 30-11-2023
A45600 | Construction of Rawalpindi Ring Road-R3(38.3 KM) Main Carriageway (MCW) from Banth (N-5) to Thalian (M-2) | RDA | HUD&PHED | North Single | 2022-03-08 | 2026-06-29 | 51 | 39 | 32997.054 | 0 | 22987.987 | 10009.067 | APPROVED 08-03-2022
A45713 | Jinnah Institute of Cardiology, Lahore | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | North Single | 2022-03-17 | 2026-06-29 | 51 | 39 | 8837.533 | 0 | 6016.076 | 2821.457 | APPROVED 17-03-2022
A46102 | Concrete Lining of Irrigation Channels to Improve Water Delivery Performance & Conveyance Efficiency-II | Irrigation | Irrigation | Punjab Based | 2022-07-01 | 2026-06-30 | 47 | 35 | 1800 | 0 | 1120.455 | 679.545 | APPROVED 28-11-2023
A46285 | Punjab affordable Housing Project (TA Component) | Punjab Housing and Town Planning Agency (PHATA) | HUD&PHED | Punjab Based | 2023-03-02 | 2028-06-13 | 63 | 27 | 3000 | 3000 | 513.581 | 2486.419 | APPROVED 13-09-2022
A46296 | Construction of Arterial Main Secondary and Distribution Network in the Areas in the Eastern Part of City (Linked with AFD Funded Extension of Water Resources in Faisalabad City Phase-II Project) | WASA Faisalabad | HUD&PHED | North Single | 2023-09-14 | 2028-06-30 | 57 | 21 | 8453.607 | 0 | 1466.07 | 6987.537 | APPROVED 13-06-2023
A46416 | Integrated Farms Development in Punjab Barani Tract by ABAD | Agency for Barani Areas Development (ABAD) | Planning & Development Board, Punjab | Multiple Region | 2022-07-01 | 2026-06-30 | 47 | 35 | 1000 | 0 | 656.6 | 343.4 | APPROVED 08-11-2022
A46458 | Program for Provision of Missing Facilities in Newly Upgraded Colleges of Nursing in Punjab | Communication & Works Department, D.G Nursing Punjab | Specialized Healthcare and Medical Education Department | Punjab Based | 2022-07-01 | 2026-06-30 | 47 | 35 | 2612.671 | 0 | 2411.792 | 200.879 | APPROVED 15-09-2023
A46554 | Establishment of Sports Complex NA-119,Lahore(LDP) | LDA | HUD&PHED | North Single | 2022-04-22 | 2027-06-30 | 62 | 38 | 1316.059 | 0 | 836.062 | 479.997 | APPROVED 22-04-2022
A46747 | Construction of Flyover Railway Line Tughlaq Town, District Multan | Roads | Communication & Works Department | South Single | 2022-05-13 | 2028-06-30 | 73 | 37 | 1437.333 | 0 | 783.264 | 654.069 | APPROVED 13-05-2022
A46904 | Construction of road from Bostal Mor at Expressway to RMK at Brewery including link to Lawrance College, Length 12.32 Km, Tehsil Murree, District Rawalpindi | Communication & Works Department | Government of Punjab | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 1077.174 | 0 | 1071.601 | 5.573 | APPROVED 11-10-2022
A47202 | National Health Support Program (NHSP) (TA Component) | Health & Population Department | Health & Population Department | Punjab Based | 2022-07-01 | 2026-12-31 | 53 | 35 | 6382.782 | 6382.782 | 534.236 | 5848.546 | APPROVED 10-02-2023
A47203 | Punjab Family Planning Program (Technical Assistance Component) | Health & Population Department | Health & Population Department | Punjab Based | 2023-07-01 | 2027-06-30 | 47 | 23 | 4282.35 | 4282.35 | 1885.05 | 2397.3 | APPROVED 23-06-2023
A47254 | Establishment of Hospital Management Information System and Queue Management Systems (PACS) in Hospitals of SHC&ME Department | Punjab Information Technology Board (PITB) | Specialized Healthcare and Medical Education Department | Punjab Based | 2022-07-01 | 2026-06-30 | 47 | 35 | 1674.054 | 0 | 1340.632 | 333.422 | APPROVED 15-09-2023
A47271 | Introduction of Hospital Waste Management Regime in Tertiary Care Hospitals in Punjab | Specialized Healthcare and Medical Education Department | Specialized Healthcare and Medical Education Department | Punjab Based | 2022-07-01 | 2026-06-30 | 47 | 35 | 1569.481 | 0 | 701.302 | 868.179 | APPROVED 12-12-2023
A47278 | Program for Provision of Bio Medical and Non-Bio Medical Equipment in Tertiary Care Hospitals in Punjab | Specialized Healthcare and Medical Education Department | Specialized Healthcare and Medical Education Department | Punjab Based | 2022-07-01 | 2025-06-28 | 35 | 35 | 1181.735 | 0 | 979.785 | 201.95 | APPROVED 01-09-2023
U47344 | Rehabilitation of Rangpur Canal System | Irrigation | Irrigation | North Single | 2022-07-01 | 2026-07-07 | 48 | 35 | 1000 | 0 | 0 | 1000 | UN-APPROVED
A47404 | Construction of Dual Carriageway from Sheikh Fazal to Chichawatni , Length-24.15 Km | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 4596.256 | 0 | 4594.256 | 2 | APPROVED 28-10-2022
A47446 | Rehabilitation / Reconstruction / Carpeting of metalled road from Rahim Yar Khan (Noor-E-Wali Railway Crossing) to Sadiq Abad (Fire Brigade office chowk) Length 20.25 Km | Communication & Works Department, Roads | Communication & Works Department, Roads | South Single | 2022-07-01 | 2028-06-30 | 71 | 35 | 1082.135 | 0 | 1081.135 | 1 | APPROVED 23-08-2022
A47476 | Widening / Improvement of Manga Raiwind Road, Length 18.00 Km. | Communication & Works Department | Government of Punjab | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 2609.289 | 0 | 1939.946 | 669.343 | APPROVED 16-09-2022
A47496 | Rehabilitation of road from Phoolnagar (Old Multan Road) to Head Balloki length 9.50 Km in District Kasur. | Roads | Roads | North Single | 2022-07-01 | 2028-06-30 | 71 | 35 | 1243.292 | 0 | 909.022 | 334.27 | APPROVED 23-09-2022
A47505 | Rehabilitation of road from Nankana Sahib to Shahkot, Length 28.00 Km in District Nankana Sahib. | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 2325.073 | 0 | 1988.067 | 337.006 | APPROVED 16-09-2022
A47507 | Rehabilitation / Restoration of Sangla Hill-Safdarabad road Length = 14.05 Km in District Nankana Sahib. | Communication & Works Department | Government of Punjab | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 1218.477 | 0 | 791.163 | 427.314 | APPROVED 16-09-2022
A47540 | Rehabilitation of Faisalabad circular road / By Pass Ring Length = 97.80 Km. | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 7064.501 | 0 | 7060.501 | 4 | APPROVED 17-10-2022
U47549 | Sialkot Ring Road Project - Land Acquisition & Shifting of utilities | Roads | Roads | North Single | 2022-07-01 | 2028-06-30 | 71 | 35 | 5953.2 | 0 | 0 | 5953.2 | UN-APPROVED
A47572 | Rehabilitation / Improvement of road from Bhowana to Aminpur road in District Chiniot Length 24.5 Km | Communication & Works Department | Government of Punjab | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 1224.97 | 0 | 1114.354 | 110.616 | APPROVED 13-10-2022
A47576 | Rehabilitation of Khushab Muzaffar Garh road Km No. 70.70 to 134.80 (District boundary Khushab to Daal More) District Jhang | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 2967.815 | 0 | 2387.12 | 580.695 | APPROVED 13-09-2022
A47593 | Rehabilitation of Akwal-Tammun-Multan Khurdh- Shah Muhammad Wali to CPEC Tarap Interchange L = 49.00 Km | Communication & Works Department | Government of Punjab | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 2616.399 | 0 | 2606.399 | 10 | APPROVED 02-09-2022
A47594 | Rehabilitation of road from Renala Khurd to Hujra Chowk via Shergarh Length 27.10 Km Tehsil Renala Khurd / Depalpur. | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 1005.887 | 0 | 1004.887 | 1 | APPROVED 30-09-2022
A47606 | Rehabilitation of Dual Carriageway Kasur Depalpur road Length 98.95 Km District Kasur & Okara | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 6997.31 | 0 | 6996.31 | 1 | APPROVED 23-09-2022
A47609 | Rehabilitation / Improvement of Lahore Jaranwala road Length 99.00 Km District Sheikhupura. | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 6995.513 | 0 | 4579.31 | 2416.203 | APPROVED 23-09-2022
A47610 | Rehabilitation of metalled road Sahiwal to Pakpattan Length 40.00 Km, District Sahiwal | Communication & Works Department, Roads | Communication & Works Department, Roads | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 4223.432 | 0 | 4091.865 | 131.567 | APPROVED 30-09-2022
A47616 | Rehabilitation of Sammundri Sahiwal road Length 50.90 Km | Communication & Works Department, Roads | Communication & Works Department, Roads | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 2189.825 | 0 | 2188.825 | 1 | APPROVED 17-10-2022
A47655 | Rehabilitation of road from Chakwal Tehsil Chowk to Balkasar Interchange via Thoa Bhadar Length = 18.00 Km District Chakwal | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 1608.511 | 0 | 1496.532 | 111.979 | APPROVED 27-09-2022
A47658 | Rehabilitation & Carpeting of road from Chirah Chowk to Karore, Length 16 Km Tehsil Kotli Sattian District Rawalpindi. | Roads | Roads | North Single | 2022-07-01 | 2028-06-30 | 71 | 35 | 1377.949 | 0 | 1176.284 | 201.665 | APPROVED 30-09-2022
A47831 | Carpet Road from Nowshera Virkan to Hafizabad via Nathu Siwiya, Buggay including khan musalman Bypass, length=31.22 Km | Communication & Works Department | Communication & Works Department | North Single | 2022-07-01 | 2025-06-30 | 35 | 35 | 1292.925 | 0 | 962.8 | 330.125 | APPROVED 03-11-2023
A47845 | Rehabilitation of Shahdara - Maqboolpura - Kala Khatai - Narang Mandi Road Length=34.11 Km in Tehsil Ferozewala District Sheikhupura | Communication & Works Department | Communication & Works Department | North Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 3515.733 | 0 | 3473.293 | 42.44 | APPROVED 11-11-2022
A48939 | Rehabilitation / Improvement of Gujrat City Roads, District Gujrat | Communication & Works Department | Communication & Works Department | North Single | 2022-10-27 | 2026-06-30 | 44 | 32 | 1190.342 | 0 | 698.032 | 492.31 | APPROVED 27-10-2022
A49249 | Construction/ Widening / Improvement of Road from Hafizabad to Gujrat via Head Khanki along L.C.C Mian Canal, Length = 45.00 Km, District Hafizabad & Gujranwala | Roads | Roads | North Single | 2022-11-21 | 2026-06-30 | 43 | 31 | 8296.554 | 0 | 3322.357 | 4974.197 | APPROVED 21-11-2022
A49371 | Re-Construction/ Construction of Road from Mianwali – D.I Khan Road at Chashma Lake to Allu Piplan Kallurkot Road i/c 4 Nos. Bridges (Old Sher Shah Soori Road), Length = 8.00 Km, District Mianwali | Roads | Roads | North Single | 2022-11-30 | 2028-06-30 | 67 | 31 | 1405.986 | 0 | 1251.156 | 154.83 | APPROVED 30-11-2022
A51217 | Establishment of Excellence Hub(s) in the field of Renewable Energy – (KFW Development Bank, Germany Assisted Project in TEVTA Punjab) | Skill Development & Entrepreneurship Department | Skill Development & Entrepreneurship Department | North Single | 2022-07-01 | 2026-06-29 | 47 | 35 | 1117.403 | 844.345 | 49.431 | 1067.972 | APPROVED 01-07-2023
A51430 | Construction of New Courts at District Headquarter Faisalabad | Communication & Works Department | Judiciary | North Single | 2022-07-01 | 2026-06-29 | 47 | 35 | 1844.126 | 0 | 1844.122 | 0.004 | APPROVED 17-03-2023
A52129 | Construction of New Courts Blocks at the Site of old Administration Block at Lahore High Court, Lahore | Communication & Works Department | Judiciary | North Single | 2023-05-31 | 2027-06-29 | 48 | 24 | 5671.377 | 0 | 2945 | 2726.377 | APPROVED 31-05-2023
A52130 | Construction of Parking Plaza at Lahore High Court, Multan Bench, Multan | Communication & Works Department | Judiciary | South Single | 2023-05-31 | 2026-06-29 | 36 | 24 | 1580.101 | 0 | 993.731 | 586.37 | APPROVED 14-10-2023
A52357 | Re-construction of Lady Willingdon Hospital, Lahore | Infrastructure Development Authority Punjab (IDAP), King Edward Medical University | Specialized Healthcare and Medical Education Department | North Single | 2023-08-21 | 2026-06-30 | 34 | 22 | 7508.45 | 0 | 4173 | 3335.45 | APPROVED 21-08-2023
A52419 | Development of a Controlled Access Corridor Facility from Niazi Interchange to to Babu Sabu Interchange Lahore | LDA | HUD&PHED | North Single | 2023-09-08 | 2026-06-30 | 33 | 21 | 11355.157 | 0 | 11354.157 | 1 | APPROVED 08-09-2023
A52466 | Rehabilitation and Development of Qila Kohna Qasim Bagh (QKQB) for the Promotion of Tourism and Preservation of Tangible and Intangible Heritage, Multan | Walled City of Lahore Authority | LG&CD Department | South Single | 2023-11-13 | 2026-06-29 | 31 | 19 | 2781.41 | 0 | 400 | 2381.41 | APPROVED 13-11-2023
A52500 | Construction of one Multistory Building for Residences Grade 11-14 for Staff Colony at Chauburji Garden Estate, Multan Road, Lahore | Communication & Works Department | S&GAD | North Single | 2023-09-07 | 2026-12-31 | 39 | 21 | 1005 | 0 | 920 | 85 | APPROVED 07-09-2023
A52501 | Construction of New GOR, Near DHA Phase-9, Lahore | Infrastructure Development Authority Punjab (IDAP) | S&GAD | North Single | 2023-11-01 | 2026-12-31 | 37 | 19 | 2130.822 | 0 | 2125.822 | 5 | APPROVED 07-09-2023
A52522 | Revamping of Lahore Zoo | Communication & Works Department, Forestry, Wildlife & Fisheries, Wildlife | Forestry,WildLife,Fisheries, Wildlife | North Single | 2023-09-20 | 2027-06-30 | 45 | 21 | 2034.648 | 0 | 1851.408 | 183.24 | APPROVED 20-09-2023
A52523 | Implementation of Master Plan of Safari Zoo Lahore | Communication & Works Department, Forestry, Wildlife & Fisheries, PHA Lahore, Wildlife | Forestry,WildLife,Fisheries | North Single | 2023-09-20 | 2027-06-30 | 45 | 21 | 2453.2 | 0 | 1968.906 | 484.294 | APPROVED 20-09-2023
D52527 | Implementation of Flood Protection Sector Project-III (FPSP-III) | Irrigation | Irrigation | Punjab Based | 2023-07-01 | 2026-06-30 | 35 | 23 | 2971 | 0 | 0 | 2971 | DROPPED 11-02-2025
A52529 | Consultancy Services for Monitoring of Development Projects / Program in Irrigation Department. | Irrigation | Irrigation | North Single | 2023-07-01 | 2026-06-30 | 35 | 23 | 1352.693 | 0 | 200 | 1152.693 | APPROVED 29-02-2024
A52584 | Rain Water Management - Drainage Arrangement for Sore Pint at Nishtar Park Sports Complex (Qaddafi Stadium), Lahore | WASA Lahore | HUD&PHED | North Single | 2023-11-01 | 2026-06-30 | 31 | 19 | 2031.584 | 0 | 1400 | 631.584 | APPROVED 08-12-2023
A55079 | Construction of 313 Residences for Police Officers/ Official (BS 1-20) at Lahore (Phase-I) | Communication & Works Department | Police Department | North Single | 2024-01-01 | 2026-12-31 | 35 | 17 | 2941.348 | 0 | 2773.267 | 168.081 | APPROVED 01-01-2024
A55128 | Integrated Master Planning and Development / Expansion of Data Darbar Complex, Including Traffic Management | Auqaf & Religious Affairs, Communication & Works Department, LDA | Auqaf & Religious Affairs | North Single | 2024-01-31 | 2027-06-30 | 40 | 16 | 6392.8 | 0 | 355.95 | 6036.85 | APPROVED 12-01-2024
A55463 | Construction of Parking Plaza along with Offices at Lahore High Court, Rawalpindi Bench, Rawalpindi | Communication & Works Department | Judiciary | North Single | 2023-10-10 | 2026-06-29 | 32 | 20 | 1972.166 | 0 | 300 | 1672.166 | APPROVED 22-09-2023
A55613 | Getting Results Access and Delivery of Quality Education Services (GRADES) | Communication & Works Department, Programme Monitoring and Implementation Unit (PMIU-PESRP), Punjab Curriculum and Textbook Board (PCTB), Punjab Education Foundation (PEF), Punjab Examination Commission (PEC), Quaid-e-Azam Academy for Educational Development (QAED), School Education Department | World Bank | Punjab Based | 2024-06-19 | 2029-06-21 | 60 | 12 | 41671.37 | 41671.37 | 0 | 41671.37 | APPROVED 30-12-2024
A55616 | Rehabilitation of Multan-Vehari Road Length 93.5 Km. | Communication & Works Department | Communication & Works Department | South Single | 2024-09-01 | 2028-06-30 | 45 | 9 | 13000 | 0 | 2000 | 11000 | APPROVED 28-06-2024
A55619 | Dualization of Faisalabad Chiniot Sargodha road from Kamalpur Interchange to Tehsil chowk Chiniot, District Faisalabad & Chiniot Length 24.00 Km. | Communication & Works Department | Communication & Works Department | North Single | 2024-03-01 | 2026-06-30 | 27 | 15 | 7575.426 | 0 | 3000 | 4575.426 | APPROVED 28-06-2024
A55622 | Establishment of Model Agriculture Malls in Punjab (2024-25 to 2025-26) | Agriculture Department | Agriculture Department | Multiple Region | 2024-04-01 | 2026-06-30 | 26 | 14 | 1171.036 | 0 | 756 | 415.036 | APPROVED 10-07-2024
A55629 | Smart Safe Cities for 19 Districts (Phase II) | Punjab Safe Cities Authority (PSCA) | Police Department | Multiple Region | 2024-07-01 | 2025-06-30 | 11 | 11 | 5645.91 | 0 | 3087.196 | 2558.714 | APPROVED 24-07-2024
U55653 | Establishment of e-Libraries for Students and General Public | Punjab Information Technology Board (PITB) | Archives & Libraries Department, Higher Education Department | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 1000 | 0 | 0 | 1000 | UN-APPROVED
A55681 | Punjab Socio Economic Registry (PSER) | Bureau of Statistics Punjab, District Administration, Punjab Information Technology Board (PITB), Punjab Social Protection Authority, Urban Unit | Planning & Development Board, Punjab | Punjab Based | 2024-07-01 | 2027-06-30 | 35 | 11 | 5112.68 | 0 | 1357.272 | 3755.408 | APPROVED 11-12-2024
A55791 | Establishment of Nawaz Sharif Institute of Cancer Treatment and Research, Lahore | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | North Single | 2024-07-01 | 2027-02-28 | 31 | 11 | 52772.52 | 0 | 14250.8 | 38521.72 | APPROVED 15-07-2024
U55848 | Initiatives to Support DLIs under National Health Support Program (NHSP) | Health & Population Department | Health & Population Department | Punjab Based | 2024-04-01 | 2025-06-30 | 14 | 14 | 1000 | 0 | 0 | 1000 | UN-APPROVED
A55881 | Developing Resilient Environment and Advancing Municipal Services (DREAMS-I) | LG&CD Department | Asian Development Bank (ADB) | Multiple Region | 2024-07-01 | 2028-06-28 | 47 | 11 | 64480.713 | 51584.517 | 5783 | 58697.713 | APPROVED 05-08-2023
A55911 | Remodeling of Jhika Gali Chowk | Communication & Works Department | Government of Punjab | North Single | 2024-09-23 | 2028-06-30 | 45 | 9 | 1795.095 | 0 | 1297.2 | 497.895 | APPROVED 28-10-2024
A55924 | Nawaz Sharif Institute of Cardiology, Sargodha | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | North Single | 2024-07-01 | 2026-01-31 | 18 | 11 | 8568.205 | 0 | 6000 | 2568.205 | APPROVED 03-05-2024
A55925 | Chief Minister’s "Plant for Pakistan" Initiative | Forestry, Transport | Forestry, Government of Punjab | Punjab Based | 2024-04-01 | 2028-06-30 | 50 | 14 | 8000 | 0 | 1800 | 6200 | APPROVED 24-04-2024
A55972 | Aquaculture: Shrimp Farming in Punjab. | Communication & Works Department, Fisheries | Forestry,WildLife,Fisheries | Multiple Region | 2024-07-01 | 2028-06-29 | 47 | 11 | 5010.352 | 0 | 896.919 | 4113.433 | APPROVED 29-07-2024
A56111 | Rehabilitation of Sahiwal Arifwala road upto District Boundary, Length = 27.00 Km, in District Sahiwal. | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 5334.124 | 0 | 2708 | 2626.124 | APPROVED 08-07-2024
A56114 | Rehabilitation / Improvement of road from Fatehjang to Pidigheb road via Dhullian Km 13 to 57.50 Length = 44.50 Tehsil Fatehjang & Pindigheb District Attock | Communication & Works Department | Communication & Works Department | North Single | 2024-09-20 | 2028-09-27 | 48 | 9 | 4703.316 | 0 | 1451 | 3252.316 | APPROVED 10-07-2024
A56115 | Rehabilitation of Sarai Chowk to Arra Rawal Road. | Communication & Works Department | Communication & Works Department | North Single | 2024-08-15 | 2028-06-30 | 46 | 10 | 1654.343 | 0 | 532 | 1122.343 | APPROVED 10-07-2024
A56116 | Rehabilitation of Talagang – Kallar Kahar – Choa Saiden Shah Road. | Communication & Works Department | Communication & Works Department | North Single | 2024-08-15 | 2028-06-30 | 46 | 10 | 5163.443 | 0 | 2287 | 2876.443 | APPROVED 10-07-2024
A56117 | Rehabilitation of That Pail road Km no.167 to 172 & from Km no.193-228. | Communication & Works Department | Government of Punjab | North Single | 2024-09-30 | 2028-06-30 | 45 | 9 | 2070.652 | 0 | 925 | 1145.652 | APPROVED 03-07-2024
A56120 | Rehabilitation of Lilla Kandwal – Katha Sagral Tehsil P.D Khan (Phase-Ii) District Jhelum & Khushab | Communication & Works Department | Communication & Works Department | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 1137.386 | 0 | 909 | 228.386 | APPROVED 10-07-2024
A56123 | Rehabilitatation of road from Bahawalnagar to Head Sulemanki Length: 75.00 Km District Bahawalnagar | Communication & Works Department | Communication & Works Department | South Single | 2024-09-02 | 2028-06-30 | 45 | 9 | 6781.311 | 0 | 1688 | 5093.311 | APPROVED 12-07-2024
A56127 | Rehabilitation of Rawalpindi Murrree Kashmir road (17-Mile to Sunny Bank). | Communication & Works Department | Communication & Works Department | North Single | 2024-07-01 | 2028-06-30 | 47 | 11 | 1281.083 | 0 | 514 | 767.083 | APPROVED 10-07-2024
A56135 | Rehabilitation of Adyala road from Khawaja Corporation to Gorukhpur | Communication & Works Department | Communication & Works Department | North Single | 2024-07-01 | 2028-06-30 | 47 | 11 | 1626.011 | 0 | 722 | 904.011 | APPROVED 10-07-2024
A56137 | Rehabilitation of road from Shahpur and Jhal Chakian to Bhalwal via Lak Morr Length (38.40+23.00) Total Length 61.40 Km in District Sargodha | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2028-06-30 | 50 | 14 | 4148.028 | 0 | 3758 | 390.028 | APPROVED 10-07-2024
A56139 | Rehabilitation of Old Klp road Sadiqabad | Communication & Works Department | Communication & Works Department | South Single | 2024-04-01 | 2028-06-30 | 50 | 14 | 1428.856 | 0 | 1102.401 | 326.455 | APPROVED 12-07-2024
A56143 | Improvement of Dehli Multan road (Section Vehari to Burewala) District Vehari | Communication & Works Department | Communication & Works Department | South Single | 2024-04-01 | 2026-06-30 | 26 | 14 | 1829.523 | 0 | 1827.523 | 2 | APPROVED 12-07-2024
A56148 | Rehabilitation / Improvement of road from Bhera Malikwal Shahpur Sahiwal road Section Jhawarian to Shahpur Length 18.50 Km District Sargodha | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2028-06-30 | 47 | 11 | 1481.194 | 0 | 713 | 768.194 | APPROVED 03-07-2024
A56149 | Rehabilitation / Improvement of Faisalabad - Jaranwala road At Makuana By-Pass to Syed Wala Okara road via Syed Wala Interchange Motorway M-3length = 45 Km | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2028-06-30 | 47 | 11 | 2060.333 | 0 | 1659.527 | 400.806 | APPROVED 08-07-2024
A56152 | Rehabilitation / Improvement of road from Soon to Barohi, Tehsil Kahuta, District Rawalpindi. | Communication & Works Department | Communication & Works Department | North Single | 2024-09-10 | 2028-06-30 | 45 | 9 | 1194.911 | 0 | 424 | 770.911 | APPROVED 10-07-2024
A56162 | Rehabilitation of G.T road from Chan Da Qila to Aziz Cross Chowk in Gujranwala City Length 12.75 Km District Gujranwala | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2028-06-30 | 50 | 14 | 5729.345 | 0 | 4046 | 1683.345 | APPROVED 10-07-2024
A56163 | Rehabilitation / Improvement of Khushab Pail Chakwal road upto District Boundary Khushab. | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2028-06-30 | 47 | 11 | 1013.507 | 0 | 675 | 338.507 | APPROVED 03-07-2024
A56164 | Rehabilitation of Jhang Bhakkar road from Mallu More to Bharairhi Km no. 231.00 to 272.00, Length 41.00 Km, District Jhang | Roads | Roads | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 3200 | 0 | 2000.725 | 1199.275 | APPROVED 04-09-2024
A56165 | Rehabilitation of Gujranwala Alipur Qadirabad road (Alipur Chowk to Kalaske) Length 14 Km District Gujranwala | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2028-06-30 | 47 | 11 | 1116.293 | 0 | 879 | 237.293 | APPROVED 05-07-2024
A56166 | Rehabilitation of Jhang T.T.Singh Chichawatni Burewala Road | Roads | Roads | North Single | 2024-08-31 | 2027-06-30 | 33 | 9 | 1560 | 0 | 964.51 | 595.49 | APPROVED 29-11-2024
A56167 | Rehabilitation of Painsra Gojra T.T.Singh Shorkot Cantt road Including Gojra and T.T.Singh By-Pass | Communication & Works Department, Roads | Communication & Works Department, Roads | North Single | 2024-07-01 | 2027-06-29 | 35 | 11 | 2467.6 | 0 | 2030.68 | 436.92 | APPROVED 10-07-2024
A56168 | Rehabalitation of road from Ellahabad to Kanganpur via Shamkot Nau I/C Ellahabad Bypass road in District Kasur | Roads | Roads | North Single | 2024-07-01 | 2028-06-30 | 47 | 11 | 1750.624 | 0 | 1178 | 572.624 | APPROVED 10-07-2024
A56170 | Rehabilitation of Sarai Alamgir Kotla Arab Ali Khan Jalal Pur Sobtian road Length 50.00 Km District Gujrat | Communication & Works Department | Communication & Works Department | North Single | 2024-09-01 | 2026-06-30 | 21 | 9 | 1255.111 | 0 | 1066.083 | 189.028 | APPROVED 10-07-2024
A56172 | Rehabilitation of Lahore -Sheikhupura- Sargodha road Length 27.00 Km District Hafizabad | Communication & Works Department | Communication & Works Department | North Single | 2024-09-01 | 2028-06-30 | 45 | 9 | 2030.289 | 0 | 2024.289 | 6 | APPROVED 10-07-2024
A56174 | Rehabilitation of Gujrat Sargodha road Km 27.90 to 122.20 (Dual Carriageway) Length 94.30 Km District M.B.Din | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2028-06-30 | 50 | 14 | 9802.059 | 0 | 1270 | 8532.059 | APPROVED 03-07-2024
A56176 | Rehabilitation of Muridke Narowal road (Section Muridke to District Boundary) Sheikhupura. | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2026-06-30 | 26 | 14 | 8698.858 | 0 | 2336 | 6362.858 | APPROVED 10-07-2024
A56177 | Rehabilitation / Re-Construction of road from Narowal to Muridke (Length Km No.0.00 to 33.21 = 33.21 Km upto District Boundary) District Narowal | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2028-06-30 | 50 | 14 | 6151.531 | 0 | 2335 | 3816.531 | APPROVED 10-07-2024
A56183 | Rehabilitation of Okara (Satghara More) to Syedwala Bridge via Satghara. | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2026-06-30 | 26 | 14 | 2453.519 | 0 | 555 | 1898.519 | APPROVED 12-07-2024
A56185 | Development of Urban Bus Depots & Allied Infrastructure, Bahawalpur | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | South Single | 2024-08-01 | 2025-06-30 | 10 | 10 | 1427.575 | 0 | 0 | 1427.575 | APPROVED 06-05-2025
A56186 | Rehabilitation / Improvement of Sahiwal – Arifwala - Bahawalnagar Road, (Section District Pakpattan) Length = 40.25 Km in District Pakpattan. | Communication & Works Department | Communication & Works Department | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 7648.025 | 0 | 3338 | 4310.025 | APPROVED 10-07-2024
A56190 | Rehabilitation / Improvement of Alternate Route to Sialkot Airport from Chand Bagh Society (Old Airport Road) to Sial Airport Including Link to Channi Gondal Chowk, Length 16.00 Km District Sialkot | Communication & Works Department | Government of Punjab | North Single | 2024-09-01 | 2028-06-30 | 45 | 9 | 1086.065 | 0 | 870.186 | 215.879 | APPROVED 05-07-2024
A56191 | Development of Urban Bus Depots & Allied Infrastructure, Faisalabad | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | North Single | 2024-08-01 | 2025-06-30 | 10 | 10 | 4304.509 | 0 | 0 | 4304.509 | APPROVED 06-05-2025
A56199 | Development of Urban Bus Depots & Allied Infrastructure, Rawalpindi | Punjab Masstransit Authority (PMA), GoPb, RDA | Transport & Masstransit Department, GoPb | North Single | 2024-04-01 | 2025-06-30 | 14 | 14 | 1576.575 | 0 | 0 | 1576.575 | APPROVED 04-03-2025
U56205 | Development of Urban Bus Depot and Allied Infrastructure at Thokar Niaz Baig, Lahore | LDA, Punjab Masstransit Authority (PMA), GoPb | Transport & Masstransit Department, GoPb | North Single | 2024-04-01 | 2025-06-30 | 14 | 14 | 8300 | 0 | 0 | 8300 | UN-APPROVED
A56206 | Development of Urban Bus Depots & Allied Infrastructure, Multan | MDA, Punjab Masstransit Authority (PMA), GoPb | Transport & Masstransit Department, GoPb | South Single | 2024-04-01 | 2025-06-30 | 14 | 14 | 1836.642 | 0 | 0 | 1836.642 | APPROVED 03-06-2025
A56209 | Construction of Residences for Officials (Grade 1-10) of Lahore High Court at Harbanspura, Lahore | Communication & Works Department | Judiciary | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 2672.082 | 0 | 10 | 2662.082 | APPROVED 18-04-2025
A56229 | Construction of Judicial Complex at District Headquarter Jhang | Communication & Works Department | Judiciary | North Single | 2024-07-01 | 2028-06-30 | 47 | 11 | 2142.679 | 0 | 250 | 1892.679 | APPROVED 11-11-2024
A56232 | Construction of Judicial Complex at Gujjar Khan, District Rawalpindi | Communication & Works Department | Judiciary | North Single | 2024-07-01 | 2028-06-30 | 47 | 11 | 1459.645 | 0 | 50 | 1409.645 | APPROVED 11-11-2024
A56305 | Establishment of Eco Tourism Facility at Lal Suhanra National Park as per International best practices (Conservation of Desert Ecosystem) | Forestry | Forestry,WildLife,Fisheries | South Single | 2024-07-01 | 2026-06-29 | 23 | 11 | 2000 | 0 | 265.258 | 1734.742 | APPROVED 11-12-2024
A56339 | Minority Development Fund | Communication & Works Department, HUD&PHED, LG&CD Department | Human Rights & Minority Affairs | Punjab Based | 2024-07-01 | 2025-06-30 | 11 | 11 | 2500 | 0 | 1100 | 1400 | APPROVED 04-03-2025
A56591 | Chief Minister Wildlife Rescue Force | Communication & Works Department, Infrastructure Development Authority Punjab (IDAP), Wildlife | Forestry,WildLife,Fisheries | Multiple Region | 2024-07-01 | 2027-06-30 | 35 | 11 | 2016.084 | 0 | 728.92 | 1287.164 | APPROVED 15-10-2024
A57003 | Livestock Asset Transfer to Rural Women in South Punjab | Livestock & Dairy Development Department | Government of Punjab | Multiple Region | 2024-07-01 | 2026-06-30 | 23 | 11 | 2000 | 0 | 1000 | 1000 | APPROVED 24-07-2024
U57230 | Construction of Cholistan Canal and its System | Irrigation | Irrigation | South Single | 2024-12-01 | 2033-06-30 | 102 | 6 | 1000 | 0 | 0 | 1000 | UN-APPROVED
U57231 | Rehabilitation and Remodeling of Main Dam, Spillway and Irrigation System of Domeli and Lehri Dam, District Jhelum | Irrigation | Irrigation | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 1350 | 0 | 0 | 1350 | UN-APPROVED
A57298 | Concrete Lining of Irrigation Channels to Improve Water Delivery Performance and Conveyance Efficiency-III | Irrigation | Irrigation | Punjab Based | 2024-07-01 | 2028-06-06 | 47 | 11 | 3995.293 | 0 | 400 | 3595.293 | APPROVED 25-11-2024
A57384 | Chief Minister Punjab Free Solar Panel Scheme | Energy Department | Energy Department | Punjab Based | 2024-07-01 | 2025-09-30 | 14 | 11 | 9975.392 | 0 | 5772.843 | 4202.549 | APPROVED 29-07-2024
A57387 | Establishment of Day Care Centers through Punjab Day Care Fund Society | Women Development Department | Women Development Department | Punjab Based | 2024-05-10 | 2027-06-30 | 37 | 13 | 1000 | 0 | 400 | 600 | APPROVED 09-05-2024
A57896 | Program for Revamping of RHCs (Phase-II) | Communication & Works Department, Health & Population Department | Health & Population Department | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 4288.956 | 0 | 2144.478 | 2144.478 | APPROVED 20-09-2024
A57897 | Program for Revamping of BHUs of North and Central Punjab (Phase-II) | Communication & Works Department, Health & Population Department | Health & Population Department | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 9594.422 | 0 | 4797.211 | 4797.211 | APPROVED 20-09-2024
A57924 | CM Punjab Laptop Program | Punjab Information Technology Board (PITB) | Higher Education Department | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 27000 | 0 | 8042 | 18958 | APPROVED 05-08-2024
A57946 | Central Punjab Non-Formal Education Project | Literacy & Non Formal Basic Education | Literacy & Non Formal Basic Education | North Single | 2024-11-01 | 2027-10-31 | 35 | 7 | 4757.198 | 0 | 911.584 | 3845.614 | APPROVED 04-03-2025
A58021 | Replacement Of Outlived Trunk Sewer From Shouq Chowk To Shaukat Khanam At Main Khayaban E Firdousi Johar Town Lahore. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2027-06-30 | 33 | 9 | 1900 | 0 | 940 | 960 | APPROVED 05-12-2024
A58083 | Chief Minister Punjab Kissan Card (2024-25 to 2025-26) | Agriculture Department | Agriculture Department | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 9000 | 0 | 2700 | 6300 | APPROVED 10-07-2024
A58090 | CM Lahore Development Program, Gulberg Zone. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 1200 | 0 | 764 | 436 | APPROVED 02-08-2024
A58091 | CM Lahore Development Program, Ravi Zone-I. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2026-06-30 | 21 | 9 | 7800 | 0 | 3147 | 4653 | APPROVED 02-08-2024
A58092 | CM Lahore Development Program, Ravi Zone-II. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2026-06-30 | 21 | 9 | 7000 | 0 | 3625 | 3375 | APPROVED 02-08-2024
A58093 | CM Lahore Development Program, Data Gunj Baksh Zone. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2026-12-31 | 27 | 9 | 4700 | 0 | 1945 | 2755 | APPROVED 02-08-2024
A58094 | CM Lahore Development Program, Samanabad Zone. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2027-06-30 | 33 | 9 | 3050 | 0 | 1432 | 1618 | APPROVED 02-08-2024
A58095 | CM Lahore Development Program, Nishter Zone-I. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2026-06-30 | 21 | 9 | 8000 | 0 | 3476 | 4524 | APPROVED 02-08-2024
A58096 | CM Lahore Development Program, Nishter Zone-II. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 7901 | 0 | 3915 | 3986 | APPROVED 02-08-2024
A58097 | CM Lahore Development Program, Shalimar Zone. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2026-06-30 | 21 | 9 | 1700 | 0 | 1047 | 653 | APPROVED 02-08-2024
A58098 | CM Lahore Development Program, Wahga Zone-I. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 9699.15 | 0 | 0 | 9699.15 | APPROVED 02-08-2024
A58099 | CM Lahore Development Program, Wahga Zone-II. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 8997.478 | 0 | 1700 | 7297.478 | APPROVED 02-08-2024
A58101 | CM Lahore Development Program, Allama Iqbal Zone. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 9600 | 0 | 0 | 9600 | APPROVED 02-08-2024
A58102 | CM Lahore Development Program, Aziz Bhatti Zone. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 8250 | 0 | 0 | 8250 | APPROVED 02-08-2024
A58237 | Chief Minister’s Program for Solarization of Agricultural Tubewells in Punjab (2024-25 to 2025-26) | Energy Department | Agriculture Department | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 8826.3 | 0 | 70 | 8756.3 | APPROVED 08-07-2024
A58266 | Apni Chhat Apna Ghar Program | Punjab Housing and Town Planning Agency (PHATA) | HUD&PHED | Punjab Based | 2024-08-12 | 2028-12-31 | 52 | 10 | 10000 | 0 | 75 | 9925 | APPROVED 12-08-2024
A58277 | Revamping of Old Blocks of Punjab Institute of Mental Health, Lahore | Communication & Works Department, Specialized Healthcare and Medical Education Department | Specialized Healthcare and Medical Education Department | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 2037.569 | 0 | 1098.411 | 939.158 | APPROVED 13-08-2024
A58363 | Revival of Citrus Sector in Punjab (2024-25 to 2027-28) | Agriculture Department | Agriculture Department | North Single | 2025-03-26 | 2028-06-30 | 39 | 3 | 1432.037 | 0 | 64 | 1368.037 | APPROVED 26-03-2025
A58390 | Restoration / Improvement of Road from Lahore Sargodha Road (Khanqah Dogran to District Boundary) Length = 9.50 Km in Tehsil Safdarabad District Sheikhupura | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 1106.356 | 0 | 255 | 851.356 | APPROVED 07-08-2024
A58500 | Restoration / Improvement of Hafizabad Khangah Dogran road | Roads | Roads | North Single | 2024-09-01 | 2027-06-30 | 33 | 9 | 1073.356 | 0 | 1067.356 | 6 | APPROVED 07-08-2024
A58520 | Restoration/ Improvement of Jhang Shorkot Kabirwala Road from Aliabad Bypass to District Boundary Jhang, Length = 64.40 Km, District Jhang | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 3647.058 | 0 | 2626.368 | 1020.69 | APPROVED 07-08-2024
A58523 | Restoration/ Improvement of Jhang Sahiwal Sargodha Road (Km No. 1.93 to 13.50 & 19.00 to 59.00), Length 51.57 Km, District Jhang | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 1777.484 | 0 | 1328.087 | 449.397 | APPROVED 07-08-2024
A58682 | Restoration / Improvement of Oudherwal Chowk to Chak Koka District Boundary | Roads | Roads | North Single | 2024-08-15 | 2028-06-30 | 46 | 10 | 1539.032 | 0 | 990 | 549.032 | APPROVED 07-08-2024
A58786 | Restoration / Improvement of metalled Road from Southern Bypass from NLC Chowk (N-5) to Bahawalpur Chowk (N-70) Length = 15.80 Km (Taken Length = 15.65 Km) District Multan | Communication & Works Department, Roads | Communication & Works Department, Roads | South Single | 2024-09-01 | 2028-06-30 | 45 | 9 | 1517.024 | 0 | 1020 | 497.024 | APPROVED 07-08-2024
A58789 | Restoration / Improvement of metalled Road from Northern Bypass from Saho Chowk (N-5) to Syedaan Wala Chowk Bosan Road District Multan Length = 9.00 Km. | Communication & Works Department, Roads | Communication & Works Department, Roads | South Single | 2024-09-01 | 2028-06-30 | 45 | 9 | 1027.522 | 0 | 713.394 | 314.128 | APPROVED 07-08-2024
A58790 | Restoration / Improvement of Road from Kabirwala Jhang Road upto District Boundary Khanewal Length = 47.00 Km (Taken Length = 40.00 Km) Tehsil Kabirwala District Khanewal. | Communication & Works Department, Roads | Communication & Works Department, Roads | South Single | 2024-09-01 | 2028-06-30 | 45 | 9 | 1644.944 | 0 | 1299 | 345.944 | APPROVED 07-08-2024
A58793 | Restoration / Improvement of Tibba Sultan Pur to Karam Pur via Mitroo Length: 44.00 District Vehari. | Communication & Works Department, Roads | Communication & Works Department, Roads | South Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 1122.512 | 0 | 804.666 | 317.846 | APPROVED 07-08-2024
A58814 | Restoration / Improvement of Shahi Road upto Bahadurpur I/C Bypass at Khanpur and R.Y Khan Sec: Channigoth-R.Y.Khan | Communication & Works Department, Roads | Communication & Works Department, Roads | South Single | 2024-09-01 | 2028-06-30 | 45 | 9 | 2506.874 | 0 | 2028.381 | 478.493 | APPROVED 07-08-2024
U58822 | Identification / Establishment of 2 Nos. Landfill Sites in Punjab | LG&CD Department | LG&CD Department | Punjab Based | 2024-07-01 | 2026-06-29 | 23 | 11 | 4500 | 0 | 0 | 4500 | UN-APPROVED
A58970 | Establishment of Cath Labs at selected DHQs and developing Allied facilities in existing buildings | Health & Population Department | Health & Population Department | Punjab Based | 2024-07-01 | 2026-12-31 | 29 | 11 | 2090.264 | 0 | 1117.44 | 972.824 | APPROVED 05-12-2024
A59027 | Reconstruction/ Rehabilitation of GT road from Quaid-e-Azam Interchange (Lahore Ring Road) to Wahga Border, District Lahore | Communication & Works Department | Government of Punjab | North Single | 2024-08-15 | 2027-06-30 | 34 | 10 | 7129.21 | 0 | 2800 | 4329.21 | APPROVED 29-07-2024
A59109 | Replacement of Old / Condemned Equipment of PFSA | Punjab Forensic Science Agency (PFSA) | Home Department | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 1000 | 0 | 987.42 | 12.58 | APPROVED 15-10-2024
A59116 | Rehabilitation / Augmentation of Comprehensive Sewerage Drainage Scheme Raiwind City, District Lahore (Phase-I) | HUD&PHED | Water Supply & Sanitation | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 1484.608 | 0 | 250 | 1234.608 | APPROVED 17-01-2025
A59117 | Rehabilitation of Comprehensive Water Supply Scheme Raiwind, District Lahore | HUD&PHED | Water Supply & Sanitation | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 1388.2 | 0 | 200 | 1188.2 | APPROVED 17-01-2025
A59157 | Establishment of Enforcement Stations of PERA in Punjab (New Construction / Rehabilitation of existing government buildings) | Communication & Works Department | S&GAD | Punjab Based | 2024-07-01 | 2027-06-30 | 35 | 11 | 9209.431 | 0 | 1000 | 8209.431 | APPROVED 19-03-2025
U59160 | Rehabilitation of Montgomery Pakpattan (M-P) Link Canal | Irrigation | Irrigation | North Single | 2024-07-01 | 2027-06-16 | 35 | 11 | 1250 | 0 | 0 | 1250 | UN-APPROVED
A59195 | South Punjab Non-Formal Education Project | Literacy & Non Formal Basic Education | Literacy & Non Formal Basic Education | South Single | 2024-11-01 | 2027-10-31 | 35 | 7 | 7555.287 | 0 | 1486.44 | 6068.847 | APPROVED 04-03-2025
A59201 | North Punjab Non-Formal Education Project | Literacy & Non Formal Basic Education | Literacy & Non Formal Basic Education | North Single | 2024-11-01 | 2027-10-31 | 35 | 7 | 5299.14 | 0 | 972.039 | 4327.101 | APPROVED 04-03-2025
A59552 | Eco-Tourism at Changa Manga and Wetlands, Uchhali & Chashma | Communication & Works Department, Wildlife | Forestry,WildLife,Fisheries | Punjab Based | 2024-07-01 | 2027-06-30 | 35 | 11 | 8710.57 | 0 | 0 | 8710.57 | APPROVED 18-04-2025
A59561 | Immersive Wildlife Experience (cinema and moving theatre) in Punjab | Wildlife | Forestry,WildLife,Fisheries | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 1719.879 | 0 | 400 | 1319.879 | APPROVED 15-10-2024
A59563 | Establishment of State of the Art Wildlife Hospital at Safari Zoo, Lahore | Communication & Works Department, Infrastructure Development Authority Punjab (IDAP), Wildlife | Forestry,WildLife,Fisheries | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 1473.731 | 0 | 253.048 | 1220.683 | APPROVED 15-10-2024
A59564 | Strengthening and Capacity Building of Wildlife Department for Conservation of Wildlife in Punjab | Wildlife | Forestry,WildLife,Fisheries | Punjab Based | 2024-07-01 | 2027-06-30 | 35 | 11 | 1000 | 0 | 87 | 913 | APPROVED 06-09-2024
A59610 | Chief Minister's Skilled Punjab Program | Punjab Skill Development Fund | Skill Development & Entrepreneurship Department | Punjab Based | 2024-07-01 | 2027-06-28 | 35 | 11 | 1445.75 | 0 | 1060.4 | 385.35 | APPROVED 28-10-2024
A59685 | Construction of Inter-Provincial Joint Check Posts (IPJCPs) in Punjab one at Attock Khurd District Attock | Communication & Works Department | Home Department | North Single | 2024-04-17 | 2026-06-30 | 26 | 14 | 1004.22 | 0 | 789.526 | 214.694 | APPROVED 26-03-2024
A59722 | Construction of Inter-Provincial Joint Check Post (IPJCPs) in Punjab one at Dajal (Punjab – KPK) District Bhakkar. | Communication & Works Department, Home Department | Home Department | North Single | 2024-07-01 | 2026-12-30 | 29 | 11 | 1175.998 | 0 | 396.099 | 779.899 | APPROVED 24-05-2024
A59746 | Rehabilitation / Improvement of Roads, Streets (P.C.C.), Sewerage / Drainage and M&R of Street Lights, Allama Iqbal-II Zone, MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-29 | 23 | 11 | 9522 | 0 | 100 | 9422 | APPROVED 02-08-2024
A59874 | Rehabilitation / Improvement of Roads, Streets (P.C.C.), Sewerage / Drainage and M&R of Street Lights, Ravi Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-11-27 | 2026-06-30 | 19 | 7 | 8350 | 0 | 2400 | 5950 | APPROVED 02-08-2024
A59875 | Rehabilitation / Improvement of Roads, Streets (P.C.C.) and M&R of Street Lights, Data Gunj Buksh Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 3677 | 0 | 900 | 2777 | APPROVED 02-08-2024
A59876 | Rehabilitation / Improvement of Roads, Streets (P.C.C.), Sewerage / Drainage and M&R of Street Lights, Samanabad Zone MC Lahore | Metropolitan Corporation Lahore | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 1251 | 0 | 400 | 851 | APPROVED 02-08-2024
A59877 | Rehabilitation / Improvement of Roads, Streets (P.C.C.), Sewerage / Drainage and M&R of Street Lights, Nishtar-I Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 8000 | 0 | 3000 | 5000 | APPROVED 02-08-2024
A59878 | Rehabilitation / Improvement of Roads, Streets (P.C.C.), Sewerage / Drainage and M&R of Street Lights, Allama Iqbal-I Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 9000 | 0 | 11.55 | 8988.45 | APPROVED 02-08-2024
A59880 | Rehabilitation / Improvement of Roads, Streets (P.C.C.), Sewerage / Drainage and M&R of Street Lights, Shalamar Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-11-27 | 2026-06-30 | 19 | 7 | 2836 | 0 | 1600 | 1236 | APPROVED 02-08-2024
A59881 | Rehabilitation / Improvement of Roads, Streets (P.C.C.), Sewerage / Drainage and M&R of Street Lights, Aziz Bhatti Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 3947 | 0 | 100 | 3847 | APPROVED 02-08-2024
A59882 | Rehabilitation / Improvement of Roads, Streets (P.C.C.), Sewerage / Drainage and M&R of Street Lights, Wahga Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 23 | 11 | 7560 | 0 | 100 | 7460 | APPROVED 02-08-2024
A59884 | Rehabilitation / Improvement of Roads, Streets (P.C.C.), Sewerage / Drainage and M&R of Street Lights, Nishtar-II Zone, MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-29 | 23 | 11 | 4000 | 0 | 1500 | 2500 | APPROVED 02-08-2024
A59892 | Provision of Wheel Chairs, Prosthetics, Hearing Aids, and other such Assistive Devices to PWDs | Social Welfare and Bait-ul-Maal Department | Social Welfare and Bait-ul-Maal Department | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 1000 | 0 | 370 | 630 | APPROVED 04-09-2024
U59907 | Establishment of Material Testing Laboratories in Gujranwala and Sialkot in Collaboration with The Urban Unit | Urban Unit | Industries, Commerce & Investment | North Single | 2024-07-01 | 2026-06-28 | 23 | 11 | 1731.213 | 0 | 0 | 1731.213 | UN-APPROVED
U59923 | SMOG Less & Climate Change Resilient Punjab | Planning & Development Board, Punjab | Planning & Development Board, Punjab | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 5000 | 0 | 0 | 5000 | UN-APPROVED
A59924 | Chief Minister Population Management and Family Planning Program | Health & Population Department | Health & Population Department | Punjab Based | 2024-08-31 | 2025-12-31 | 16 | 9 | 1000 | 0 | 173.634 | 826.366 | APPROVED 04-09-2024
A59926 | Establishment of Garment Cities in Punjab | Communication & Works Department, Energy Department, Forestry, Wildlife & Fisheries, Punjab Industrial Estates Development & Management Company (PIEDMC), Technical Education & Vocational Training Authority (TEVTA) | Industries, Commerce & Investment | North Single | 2024-07-01 | 2026-06-29 | 23 | 11 | 3877.864 | 0 | 2524.444 | 1353.42 | APPROVED 24-07-2024
A59929 | CM Punjab Green Credit Program | Environment Protection & Climate Change Department | Environment Protection & Climate Change Department | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 1000 | 0 | 151.2 | 848.8 | APPROVED 06-09-2024
A59930 | CM Initiative for Agro Forestry for Forest Waste Land | Forestry, Wildlife & Fisheries | Forestry,WildLife,Fisheries | Punjab Based | 2024-07-01 | 2027-06-30 | 35 | 11 | 1000 | 0 | 904.716 | 95.284 | APPROVED 29-07-2024
A59938 | Rain Water Management - Drainage Arrangement for Sore Point at Tajpura B-Block, Lahore | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 1046.186 | 0 | 552 | 494.186 | APPROVED 24-12-2024
U59944 | Establishment of Mian Nawaz Sharif Engineering & Technology University, Kasur | Industries, Commerce & Investment | Industries, Commerce & Investment | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 9500 | 0 | 0 | 9500 | UN-APPROVED
A59988 | Rehabilitation / Improvement of Pail Chowk to Uchali Road Length=55 KM District Khushab | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2028-06-30 | 47 | 11 | 3091.377 | 0 | 1100 | 1991.377 | APPROVED 18-10-2024
A60018 | Construction of Flyover at Khawaja Corporation at Adyala Road, District Rawalpindi. | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 3407.306 | 0 | 2113 | 1294.306 | APPROVED 26-08-2024
A60020 | Construction of Underpass at GPO Chowk & TM Chowk on Mall Road Including Pedestrain Underpass near AFIC, District Rawalpindi | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 4388.286 | 0 | 4370.286 | 18 | APPROVED 25-11-2024
A60025 | CM Punjab: Livestock Card | Livestock & Dairy Development Department | Government of Punjab | Punjab Based | 2024-07-01 | 2026-06-30 | 23 | 11 | 4382.08 | 0 | 507.64 | 3874.44 | APPROVED 24-07-2024
U60033 | Construction of Narowal Medical College | Specialized Healthcare and Medical Education Department | Specialized Healthcare and Medical Education Department | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 6000 | 0 | 0 | 6000 | UN-APPROVED
A64744 | Capacity Building Project for Performance Improvement of the Lahore and Faisalabad Water and Sanitation Agencies, Punjab | HUD&PHED | HUD&PHED | North Single | 2024-12-04 | 2027-06-30 | 30 | 6 | 4238.85 | 3893.85 | 0 | 4238.85 | APPROVED 01-07-2025
A64843 | Rainwater Harvesting Project for Murree District | LG&CD Department | LG&CD Department | North Single | 2024-10-07 | 2026-06-30 | 20 | 8 | 1163.36 | 0 | 442.32 | 721.04 | APPROVED 07-10-2024
A65099 | Construction of Additional Carriageway (Dehli - Multan Road) from Pull 114/16-R to Pir Murad Morr, Length=50.60KM, District Vehari | Communication & Works Department | Government of Punjab | South Single | 2024-10-31 | 2028-06-30 | 43 | 7 | 8499.48 | 0 | 2200 | 6299.48 | APPROVED 24-12-2024
A65395 | Specialized Medical Equipment for Jinnah Institute of Cardiology, Lahore | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | North Single | 2024-12-01 | 2026-03-17 | 15 | 6 | 6889.162 | 0 | 2333.6 | 4555.562 | APPROVED 29-01-2025
A65455 | Punjab Smog Mitigation And Response Initiative – Air Safe | Environment Protection & Climate Change Department | Environment Protection & Climate Change Department | Punjab Based | 2024-11-14 | 2026-06-30 | 19 | 7 | 5381 | 0 | 2000 | 3381 | APPROVED 15-11-2024
A65479 | Construction of Flyover at GT Road - Chan Da Qila Chowk, District Gujranwala | Communication & Works Department | Government of Punjab | North Single | 2024-11-30 | 2028-06-30 | 43 | 7 | 1735.361 | 0 | 800 | 935.361 | APPROVED 03-01-2025
A65526 | Providing and Laying Trunk Sewer from Model Bazar Jhang Road to Dijkot Drain Disposal & Improvement of Sewerage System in Saifabad, Faisalabad | WASA Faisalabad | HUD&PHED | North Single | 2024-12-06 | 2027-12-06 | 36 | 6 | 1199.48 | 0 | 100 | 1099.48 | APPROVED 21-02-2025
A65527 | Upgradation and Rehabilitation of Pumping Station No.34 and Installation of 36” HDPE Forcemain in Samanabad, Faisalabad | WASA Faisalabad | HUD&PHED | North Single | 2024-12-06 | 2027-06-30 | 30 | 6 | 1048 | 0 | 70 | 978 | APPROVED 21-02-2025
A65528 | Providing and Laying of HDPE Forcemain from Dawood Chowk Disposal Station to Fish Farm Satyana Road, Faisalabad | WASA Faisalabad | HUD&PHED | North Single | 2024-12-06 | 2027-07-30 | 31 | 6 | 1249.15 | 0 | 0 | 1249.15 | APPROVED 18-04-2025
U65529 | Providing and Laying of Forcemain and Development of the Sewerage System in adjacent areas of Gatti, Aslam Park, Farooq Town, Adnan Town, Bagewala Road, Azhar Town, Sufyan Town and Adjoining Areas | WASA Faisalabad | HUD&PHED | North Single | 2024-12-06 | 2027-06-30 | 30 | 6 | 1250 | 0 | 0 | 1250 | UN-APPROVED
A65564 | Revamping of Bansara Gali Zoological Garden, Murree | Forestry, Wildlife & Fisheries | Forestry,WildLife,Fisheries | North Single | 2024-07-01 | 2027-06-30 | 35 | 11 | 3915.598 | 0 | 474.076 | 3441.522 | APPROVED 04-02-2025
A65819 | Construction of Additional Carriageway (Dehli-Multan Road) from babar Chowk to Drammawala Morr, Length=19.20 Km | Communication & Works Department | Communication & Works Department | South Single | 2024-12-17 | 2028-06-30 | 42 | 6 | 3108 | 0 | 1000 | 2108 | APPROVED 17-12-2024
A65866 | Replacement of Old / Condemned Equipment of PFSA (Phase-II) | Punjab Forensic Science Agency (PFSA) | Home Department | North Single | 2024-12-17 | 2026-06-30 | 18 | 6 | 3414.5 | 0 | 0 | 3414.5 | APPROVED 09-04-2025
A65877 | Construction of 03 Towers for Multistorey Building for Residences of Government Officials at Chauburji Garden Estate, Multan Road, Lahore | Communication & Works Department | S&GAD | North Single | 2024-12-19 | 2026-12-19 | 24 | 6 | 3125.424 | 0 | 0 | 3125.424 | APPROVED 19-12-2024
A65920 | Construction of Administrative Tower-A at Old P&D Building site, Lahore | Infrastructure Development Authority Punjab (IDAP) | S&GAD | North Single | 2025-04-01 | 2027-06-30 | 26 | 2 | 4020.401 | 0 | 2000 | 2020.401 | APPROVED 14-02-2025
A65957 | Community Empowerment and Strengthening of Healthcare Access through Maryam Nawaz Health Clinic | Health & Population Department | Health & Population Department | Punjab Based | 2025-02-01 | 2026-06-30 | 16 | 4 | 9031.286 | 0 | 343.7 | 8687.586 | APPROVED 09-05-2025
A66061 | CM Punjab Asaan Karobar Finance | Punjab Small Industries Corporation (PSIC) | Industries, Commerce & Investment | Punjab Based | 2025-01-01 | 2032-06-30 | 89 | 5 | 9500 | 0 | 550 | 8950 | APPROVED 12-02-2025
A66062 | CM Punjab Asaan Karobar Card | Punjab Small Industries Corporation (PSIC) | Industries, Commerce & Investment | Punjab Based | 2025-01-01 | 2030-06-30 | 65 | 5 | 9500 | 0 | 500 | 9000 | APPROVED 12-02-2025
A66250 | Comprehensive Door-to-Door Socio-Economic Survey of Punjab For Establishing Punjab Socio-Economic Registry (PSER)-PC-II | Planning & Development Board, Punjab | Planning & Development Board, Punjab | Punjab Based | 2025-02-19 | 2026-06-02 | 15 | 4 | 7774.314 | 0 | 158 | 7616.314 | APPROVED 19-02-2025
A67015 | Dualization of Road from Toba Tek Singh Interchange (M-4) to Rajana Interchange (M-3), Length=26.44 Km, District T.T.Singh | Communication & Works Department | Communication & Works Department | North Single | 2025-03-10 | 2028-06-30 | 39 | 3 | 7770.948 | 0 | 2000 | 5770.948 | APPROVED 10-03-2025
U67213 | Rehabilitation/ Re-Construction/ Improvement of Road from Pasrur to Kingra Village via Burhanpur, Chahiye Wali, Balaggan, Hargan, Shahzada, Seowal, Jhatoky, Mandi Throo, Khanpur, Syedan & Sabaz Kot (Total Length=29.70KM), District Sialkot | Communication & Works Department | Communication & Works Department | North Single | 2025-03-31 | 2028-06-30 | 38 | 2 | 1529.442 | 0 | 0 | 1529.442 | UN-APPROVED
A67295 | Construction of Punjab Revenue Authority (PRA) Headquarter | Infrastructure Development Authority Punjab (IDAP), Public Buildings | Finance Department | North Single | 2025-03-14 | 2026-06-30 | 15 | 3 | 4023 | 0 | 2000 | 2023 | APPROVED 14-03-2025
U67647 | Establishment of 50 Bedded Hospital in Bhurban, Murree | Communication & Works Department, Health & Population Department | Health & Population Department | North Single | 2025-03-01 | 2027-06-30 | 27 | 3 | 1441.642 | 0 | 0 | 1441.642 | UN-APPROVED
A68035 | Rehabilitation/ Reconstruction/ Widening of Road from N-5 (Ghousia Chowk) to-Lodhran — Jalalpur Road (Jindu Morr) Via DC Office & Pathanwala including Construction of Flyover at Pathanwala Railway Crossing, Length=3.00km, District Lodhran | Communication & Works Department | Roads | South Single | 2025-03-24 | 2028-06-30 | 39 | 3 | 2548.03 | 0 | 0 | 2548.03 | APPROVED 24-03-2025
A69527 | Widening of Road from District Complex to Kakuwal Bridge along Gujrat Branch including Flyover, District Mandi Baha-ud-Din | Communication & Works Department | Communication & Works Department | North Single | 2025-05-06 | 2028-06-30 | 37 | 1 | 1864.44 | 0 | 0 | 1864.44 | APPROVED 06-05-2025
A69528 | Construction of Road from Kakuwal Bridge to Kuthyala Syedan via Baha-ud-Din Kot Baloach Drain including Flyover on Railway Line, District Mandi Baha-ud-Din | Communication & Works Department | Communication & Works Department | North Single | 2025-05-06 | 2028-06-30 | 37 | 1 | 3134.183 | 0 | 0 | 3134.183 | APPROVED 06-05-2025
U69642 | Construction and Laying of RCC Sewerage and Drainage System in Mohallah Islamabad, Jinnah Colony, Niaz Mira, Haveli Mir Din, Sabir Town & Allied Abadies (Phase-II), District Lahore | HUD&PHED | LG&CD Department | North Single | 2025-05-01 | 2027-06-30 | 25 | 1 | 1695.333 | 0 | 0 | 1695.333 | UN-APPROVED
A70258 | IPF Component for Punjab Clean Air Program (PCAP) | Punjab Resource Management & Policy Unit (PRMPU) | Planning & Development Board, Punjab | Punjab Based | 2025-05-22 | 2030-06-30 | 61 | 1 | 5700.351 | 5700.351 | 0 | 5700.351 | APPROVED 22-05-2025
A70353 | Transformation of Punjab Resource Management & Policy Unit (PRMPU) | Punjab Resource Management & Policy Unit (PRMPU) | Planning & Development Board, Punjab | Punjab Based | 2025-05-17 | 2030-06-30 | 61 | 1 | 2046 | 0 | 0 | 2046 | APPROVED 17-05-2025
A00454 | Construction of Tamman Dam | Irrigation | Irrigation | North Single | 2014-10-16 | 2025-07-30 | 129 | 128 | 4232.795 | 0 | 2906.934 | 1325.861 | APPROVED 16-10-2014
A00968 | Establishment of Govt. General Hospital at Chak No.224/RB, Faisalabad. | District Health Authority, Health & Population Department, Provincial Buildings Division | Health & Population Department | North Single | 2015-06-03 | 2025-06-30 | 120 | 120 | 2421.432 | 0 | 1662.346 | 759.086 | APPROVED 03-06-2015
A23753 | PC-1 for Remaining Land Acquisition for GTC Project | Irrigation | Irrigation | Multiple Region | 2018-07-01 | 2025-07-31 | 84 | 83 | 8171.031 | 0 | 4642.195 | 3528.836 | APPROVED 28-01-2020
A34175 | Establishment of 200 Bedded Mother & Child Hospital in District Attock | Infrastructure Development Authority Punjab (IDAP) | Federal Fund, Health & Population Department | North Single | 2021-03-15 | 2025-07-14 | 51 | 51 | 5320.01 | 0 | 4820.01 | 500 | APPROVED 11-01-2021
A34477 | Establishment of Surgical City at Sialkot. | Punjab Small Industries Corporation (PSIC) | Industries, Commerce & Investment | North Single | 2021-07-01 | 2026-06-30 | 59 | 47 | 1721.729 | 0 | 1109.614 | 612.115 | APPROVED 14-12-2021
A37225 | Institutional Strengthening of P&D Board and Capacity Building of Public Sector Employees | Planning & Development Board, Punjab, Punjab Resource Management & Policy Unit (PRMPU) | Planning & Development Board, Punjab | North Single | 2021-07-01 | 2026-06-29 | 59 | 47 | 2637.012 | 0 | 1177.649 | 1459.363 | APPROVED 04-11-2021
A42788 | Establishment of 50 Bedded Mother and Child Hospital in Tehsil Kot Adu, District Muzaffargarh | Health & Population Department | Health & Population Department | South Single | 2021-07-01 | 2023-06-30 | 23 | 47 | 1009.088 | 0 | 625.403 | 383.685 | APPROVED 03-12-2021
A42817 | Up-gradation of DHQ Hospital Bhakkar, District Bhakkar | Health & Population Department | Health & Population Department | North Single | 2021-07-01 | 2025-06-30 | 47 | 47 | 1525.873 | 0 | 514.122 | 1011.751 | APPROVED 04-11-2021
A45909 | Providing River Training Works for protection of Link 1 in DG Khan | Irrigation | Irrigation | South Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 1464.712 | 0 | 116.897 | 1347.815 | APPROVED 18-11-2022
A56323 | GIS Based Protection Regime and Establishment of Digital Communication Cell in Forestry, Wildlife and Fisheries Department | Forestry, Wildlife & Fisheries | Forestry,WildLife,Fisheries | Punjab Based | 2024-07-01 | 2027-06-30 | 35 | 11 | 1200 | 0 | 505.514 | 694.486 | APPROVED 06-09-2024
A65837 | Construction of DC Complex and District Emergency Operation Center (DEOC), District Kot Addu | Communication & Works Department | BOR | South Single | 2024-12-18 | 2025-12-17 | 11 | 6 | 1300.136 | 0 | 0 | 1300.136 | APPROVED 18-12-2024
A65838 | Construction of DC Complex and District Emergency Operation Center (DEOC), District Murree | Communication & Works Department | BOR | North Single | 2024-12-18 | 2025-12-17 | 11 | 6 | 1000 | 0 | 0 | 1000 | APPROVED 18-12-2024
A70284 | Induction of Eco-Friendly Buses in Rajanpur | Transport & Masstransit Department, GoPb | Transport | South Single | 2025-05-23 | 2026-06-30 | 13 | 1 | 1005.908 | 0 | 0 | 1005.908 | APPROVED 03-06-2025
U70285 | Development of Urban Bus Depots & Allied Infrastructure in Rajanpur | Transport & Masstransit Department, GoPb | Transport | South Single | 2025-05-23 | 2026-06-30 | 13 | 1 | 1800 | 0 | 0 | 1800 | UN-APPROVED
U70318 | Development of Urban Bus Depot and Allied Infrastructure at Railway Station, Lahore | Transport & Masstransit Department, GoPb | Transport & Masstransit Department, GoPb | North Single | 2025-05-25 | 2026-06-30 | 13 | 1 | 1800 | 0 | 0 | 1800 | UN-APPROVED
A70851 | Induction of Eco-Friendly Buses in Faisalabad Division | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | North Single | 2025-06-03 | 2027-06-30 | 24 | 0 | 4285.656 | 0 | 0 | 4285.656 | APPROVED 03-06-2025
A70852 | Induction of Eco-Friendly Buses in Sahiwal Division | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | North Single | 2025-06-03 | 2027-06-30 | 24 | 0 | 5621.716 | 0 | 0 | 5621.716 | APPROVED 03-06-2025
A70856 | Induction of Eco-Friendly Buses in Multan Division | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | South Single | 2025-06-03 | 2027-06-30 | 24 | 0 | 2748.889 | 0 | 0 | 2748.889 | APPROVED 03-06-2025
A70857 | Induction of Eco-Friendly Buses in Rawalpindi Division | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | North Single | 2025-06-03 | 2027-06-30 | 24 | 0 | 4872.645 | 0 | 0 | 4872.645 | APPROVED 03-06-2025
A70858 | Induction of Eco-Friendly Buses in Gujrat Division | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | North Single | 2025-06-03 | 2027-06-30 | 24 | 0 | 5953.891 | 0 | 0 | 5953.891 | APPROVED 03-06-2025
A70859 | Induction of Eco-Friendly Buses in Gujranwala Division | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | North Single | 2025-06-03 | 2027-06-30 | 24 | 0 | 8411.586 | 0 | 0 | 8411.586 | APPROVED 03-06-2025
A70860 | Induction of Eco-Friendly Buses in Sargodha Division | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | North Single | 2025-06-03 | 2027-06-30 | 24 | 0 | 6320.461 | 0 | 0 | 6320.461 | APPROVED 03-06-2025
A70861 | Induction of Eco-Friendly Buses in Bahawalpur Division | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | South Single | 2025-06-03 | 2027-06-30 | 24 | 0 | 2764.51 | 0 | 0 | 2764.51 | APPROVED 03-06-2025
A70862 | Induction of Eco-Friendly Buses in Dera Ghazi Khan Division | Punjab Transport Company (PTC), GoPb | Transport & Masstransit Department, GoPb | South Single | 2025-06-03 | 2027-06-30 | 24 | 0 | 6742.686 | 0 | 0 | 6742.686 | APPROVED 03-06-2025
A00008 | Construction of Small Dams in District Attock Phase II Shahbazpur, Tajabara and Sadrial Dams (Revised) | Irrigation | Irrigation | North Single | 2007-11-19 | 2025-07-31 | 212 | 211 | 1168.58 | 0 | 457.02 | 711.56 | APPROVED 19-11-2007
A00049 | Construction of Small Dams in District Chakwal Phase II (Dhok Hum, Mundi Dam, Dhok Jhang and Uthwal /Lakhwal Dam (Revised) | Irrigation | Irrigation | North Single | 2010-03-19 | 2025-07-31 | 184 | 183 | 1496.08 | 0 | 971.01 | 525.07 | APPROVED 19-03-2010
A00920 | Sewerage System from Larechs Colony to Gulshan-e-Ravi, Lahore. | WASA Lahore | HUD&PHED | North Single | 2020-06-25 | 2028-06-30 | 96 | 60 | 14165.06 | 14165.06 | 231.911 | 13933.149 | APPROVED 16-03-2020
A03288 | Establishment of 100-Bedded Mother and Child Hospital, Murree (for Conversion into General Hospital) | Infrastructure Development Authority Punjab (IDAP), Specialized Healthcare and Medical Education Department | Health | North Single | 2017-07-01 | 2026-06-28 | 107 | 95 | 4157.511 | 0 | 600 | 3557.511 | APPROVED 20-06-2017
A04593 | Storm Water Drainage System from Haji Camp to River Ravi via Laxmi Chowk, McLeod Road, Nabha Road, Chauburji and Sham Nagar, Lahore. | WASA Faisalabad | HUD&PHED | North Single | 2016-10-20 | 2027-06-30 | 128 | 104 | 4066.653 | 0 | 3646.996 | 419.657 | APPROVED 15-07-2016
A04605 | Extension of Water Resources Faisalabad City Phase II (French Funded). | WASA Faisalabad | HUD&PHED | North Single | 2021-09-20 | 2028-09-30 | 84 | 45 | 14636.928 | 11790.413 | 4254.5 | 10382.428 | APPROVED 24-11-2017
A11426 | Construction of Mujahid Dam District Rawalpindi | Irrigation | Irrigation | North Single | 2009-09-07 | 2026-06-30 | 201 | 189 | 1790.166 | 0 | 572.063 | 1218.103 | APPROVED 07-09-2009
A11458 | Establishment of Sports Complex at Rakh Shahdra Lahore (LDP) | LDA | HUD&PHED | North Single | 2017-07-01 | 2028-06-30 | 131 | 95 | 1373.539 | 0 | 940.247 | 433.292 | APPROVED 14-07-2017
A11462 | Establishment of Sports Complex Singh Pura, Lahore (LDP). | LDA | HUD&PHED | North Single | 2017-07-01 | 2028-06-30 | 131 | 95 | 1559.344 | 0 | 1223.977 | 335.367 | APPROVED 14-07-2017
A11466 | Establishment of Sports Complex at Gurumangat Road NA-126, Lahore (LDP). | LDA | HUD&PHED | North Single | 2017-07-01 | 2028-06-30 | 131 | 95 | 1871.141 | 0 | 1362.321 | 508.82 | APPROVED 14-07-2017
A11467 | Establishment of Sports Complex Canal Bank near EME Society,Lahore(LDP). | LDA | HUD&PHED | North Single | 2017-07-01 | 2028-06-30 | 131 | 95 | 1559.457 | 0 | 1243.179 | 316.278 | APPROVED 14-07-2017
A11469 | Establishment of Sports Complex Shalamar Lahore (LDP). | LDA | HUD&PHED | North Single | 2017-07-01 | 2027-06-30 | 119 | 95 | 2562.76 | 0 | 1068.542 | 1494.218 | APPROVED 14-07-2017
A47199 | Establishment of Cadet College at District Multan | Communication & Works Department | School Education Department | South Single | 2022-07-01 | 2026-06-30 | 47 | 35 | 1678.669 | 0 | 461.924 | 1216.745 | APPROVED 25-08-2023
Formulas:
OD = DATEDIF([Plan Start], [Plan Finish], "m")
AD = DATEDIF([Plan Start], DATEVALUE("30-06-2025"), "m")