## Sheet3
Project ID | Project | Project Manager | Organization | Region | Plan Start | Plan Finish | OD | AD | BAC | Foreign | AC | ETC
130 | Establishment of Fatima Jinnah Institute of Dental Sciences- Jubilee Town- Lahore | Communication & Works Department- Punjab Information Technology Board (PITB) | Specialized Healthcare and Medical Education Department | North Single | 2013-04-01 | 2026-06-30 | 161 | 74.5667 | 4480.577 | 0 | 3801.188 | 0
989 | Flood Protection of Sialkot against Aik- Bhed- and Palkhu Nullah | Irrigation | Irrigation | North Single | 2015-06-10 | 2026-06-30 | 135 | 61.2333 | 4787.145 | 0 | 3643.68 | 1043.465
2194 | Energy Efficiency & Conservation Programme (PGDP- DLI-5) | Energy Department- Punjab Energy Efficiency & Conservation Agency | Energy Department | Punjab Based | 2020-12-18 | 2026-06-30 | 67 | 27.6 | 3615.016 | 0 | 3500 | 0
2607 | Land Acquisition for Jalalpur Irrigation Project | Irrigation | Irrigation | North Single | 2016-01-05 | 2025-07-31 | 117 | 57.75 | 3663.95 | 0 | 3662.95 | 0
3293 | Enhanced HIV / AIDS Control Programme Punjab (3 Years) (Phase-II) | Directorate General Health Services Punjab- Health- Health & Population Department | Health & Population Department | Punjab Based | 2016-07-01 | 2026-06-30 | 122 | 54.7833 | 3829.871 | 0 | 2976.339 | 0
4013 | Punjab Intermediate Cities Improvement Investment Prgramme | LG&CD Department | Government of Punjab | North Single | 2016-07-01 | 2026-06-25 | 122 | 54.7833 | 62280.9 | 1 | 37361 | 14263.201
4518 | Construction of Dadhocha Dam | Government of The Punjab- Irrigation | Government of Punjab- Planning & Development Board- Punjab | North Single | 2017-07-01 | 2026-07-18 | 110 | 48.7 | 14454.256 | 0 | 9233.826 | 3800.43
4707 | Punjab Tourism For Economic Growth Project (PTEGP) - World Bank Assisted | Planning & Development Board- Punjab | Planning & Development Board- Punjab | Punjab Based | 2017-10-10 | 2025-06-30 | 94 | 47.0167 | 8525 | 1 | 8000 | 125
6350 | Southern Punjab Poverty Alleviation Project (SPPAP)-IFAD Assisted | Planning & Development Board- Punjab | Planning & Development Board- Punjab | Multiple Region | 2011-09-30 | 2028-03-31 | 201 | 83.7167 | 25243.13 | 1 | 20017.553 | 665.445
6822 | Upscaling of Green Pakistan Program | Forestry- Wildlife & Fisheries | Government of Punjab | Punjab Based | 2016-07-01 | 2028-06-30 | 146 | 54.7833 | 13187.629 | 0 | 8287.629 | 4850
7189 | Upgradation and Environmental Improvement of Chungi No. 09 Disposal Station Multan. | WASA Multan | HUD&PHED | South Single | 2021-12-24 | 2027-06-30 | 67 | 21.4167 | 3432.84 | 0 | 2630.625 | 452.215
7434 | Extension and Rehabilitation of Qutab Drain | Irrigation | Irrigation | South Single | 2017-07-01 | 2025-07-31 | 98 | 48.7 | 3620.171 | 0 | 1902.329 | 1717.642
7608 | Construction of Jalalpur Irrigation Project and its System | Irrigation | Irrigation | North Single | 2018-07-01 | 2026-06-29 | 97 | 42.6167 | 32721.46 | 1 | 21350.094 | 251.366
8295 | Ten Billion Tree Tsunami Programme (Phase-1) Up-scaling of Green Pakistan Programme (Revised) | Communication & Works Department- Fisheries- Forestry- Wildlife | Federal Fund- Government of Punjab | Punjab Based | 2016-07-01 | 2025-06-30 | 110 | 54.7833 | 2945.3 | 0 | 1554.277 | 1381.023
10125 | Channelization of Deg Nullah (Land Acquisition Punjab Component) | Irrigation | Irrigation | North Single | 2016-11-30 | 2025-07-31 | 106 | 52.25 | 3175.485 | 0 | 3174.485 | 0
11979 | Construction of Building of Women University- Sialkot on acquired piece of land at Sialkot | Higher Education Department | Higher Education Department | North Single | 2017-02-10 | 2026-06-30 | 114 | 51.05 | 2946.888 | 0 | 2018.291 | 848.597
24313 | Addition / Alteration & Improvement Works in GORs- Lahore | Communication & Works Department | S&GAD | North Single | 2023-07-01 | 2026-06-30 | 37 | 12.1833 | 3400 | 0 | 3059.206 | 190.794
24316 | Renewable Energy Development Sector Investment Programme (REDSIP) | Energy Department | Energy Department | North Single | 2013-11-07 | 2026-06-30 | 154 | 70.9 | 12861 | 0 | 11478.808 | 1331.192
24627 | PPIC3 Rawalpindi | Communication & Works Department- Punjab Information Technology Board (PITB)- Punjab Safe Cities Authority (PSCA) | Police Department | North Single | 2017-04-01 | 2025-12-30 | 107 | 50.2167 | 5251.294 | 0 | 3537.781 | 0
24630 | PPIC3 Faisalabad | Communication & Works Department- Punjab Information Technology Board (PITB)- Punjab Safe Cities Authority (PSCA) | Police Department | North Single | 2017-01-06 | 2025-12-30 | 109 | 51.6333 | 4215.603 | 0 | 3375.266 | 0
24631 | PPIC3 Gujranwala | Communication & Works Department- Punjab Information Technology Board (PITB)- Punjab Safe Cities Authority (PSCA) | Police Department | North Single | 2017-01-06 | 2025-12-30 | 109 | 51.6333 | 4182.549 | 0 | 3009.552 | 0
25292 | Lahore Water and Waste Water Management Project - Construction of Surface Water Treatment Plant at BRBD Canal Lahore. | WASA Lahore | HUD&PHED | North Single | 2018-09-15 | 2028-06-30 | 119 | 41.35 | 21045.71 | 1 | 119.345 | 20633.465
25616 | Punjab Rozgar | Punjab Small Industries Corporation (PSIC) | Industries- Commerce & Investment | Punjab Based | 2020-04-01 | 2026-06-29 | 76 | 31.95 | 10000 | 0 | 4790.246 | 4509.754
26186 | Rehabilitation and Modernization of Islam Barrage | Irrigation | Irrigation | South Single | 2019-12-31 | 2025-12-31 | 73 | 33.4833 | 2993.18 | 1 | 4801.266 | 0
26215 | Establishment of 200 Bedded Mother & Child Hospital in District Layyah | Infrastructure Development Authority Punjab (IDAP) | Federal Fund- Health & Population Department | South Single | 2021-03-15 | 2025-07-14 | 53 | 26.15 | 5944.228 | 0 | 5444.228 | 0
26216 | Establishment of 300-Bedded DHQ Hospital Mianwali (New Block) | Infrastructure Development Authority Punjab (IDAP) | Health & Population Department | North Single | 2019-07-30 | 2025-06-30 | 72 | 36.05 | 7997.45 | 0 | 7996.45 | 0
27463 | Construction of MPA Hostel Lahore Phase II | Communication & Works Department | Provincial Assembly | North Single | 2019-07-01 | 2027-06-30 | 97 | 36.5333 | 6296.749 | 0 | 2480.684 | 2816.065
28143 | Establishment of Tertiary Care Hospital (Nishtar -II)- Multan | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | South Single | 2019-07-01 | 2026-06-30 | 85 | 36.5333 | 13368.643 | 0 | 9992.602 | 2957.041
28430 | Construction of four(04) sewage treatment plants and required sewerage lines under Phase-I(Rawal Lake and its surroundings including the Catchment area. 36% GoPb share) | WASA Rawalpindi | HUD&PHED | North Single | 2019-03-01 | 2026-06-30 | 89 | 38.5667 | 5244.7 | 0 | 0 | 5243.7
28453 | Establishment of Teaching Hospital (Sheikh Zayed-II)- Rahim Yar Khan | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | South Single | 2019-07-01 | 2026-06-30 | 85 | 36.5333 | 7066.9 | 0 | 3440 | 3376.9
28611 | Construction of Eastern Wastewater Treatment Plant 33 MGD of Faisalabad City Phase-I (DANIDA Assisted). | WASA Faisalabad | HUD&PHED | North Single | 2020-07-28 | 2030-08-31 | 123 | 29.9833 | 56036.79 | 1 | 366.291 | 37954.849
28867 | Dualization of Muzaffargarh Road (Jauharabad – Chowk Girote)- Length 25 Km- District Khushab | Communication & Works Department | Communication & Works Department | North Single | 2019-07-01 | 2028-06-30 | 110 | 36.5333 | 3460.093 | 0 | 2390.602 | 992.491
29597 | Heritage and Urban Regeneration in Lahore Fort (AFD Funded) | LG&CD Department | LG&CD Department | North Single | 2022-07-07 | 2027-07-06 | 61 | 18.1667 | 4036.59 | 1 | 540 | 2812.791
29674 | Establishment of University of Child Health Sciences at Lahore | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | North Single | 2021-07-01 | 2026-06-29 | 61 | 24.35 | 4265.753 | 0 | 1500 | 2265.753
29687 | Punjab Agriculture Food and Drug Authority | Infrastructure Development Authority Punjab (IDAP) | Home Department | North Single | 2018-07-01 | 2025-06-30 | 85 | 42.6167 | 15610.27 | 0 | 15610.265 | 0
29722 | Program to Uplift Water Supply & Sanitation Infrastructure in Underdeveloped Areas of Punjab. | Water Supply & Sanitation | HUD&PHED | Punjab Based | 2019-07-01 | 2026-06-30 | 85 | 36.5333 | 3608.639 | 0 | 3206.036 | 229.877
29781 | Construction of Punjab Judicial Academy at Kala Shah Kaku Lahore (Phase-II) | Communication & Works Department | Law & Parliamentary Affairs | North Single | 2019-07-01 | 2025-06-30 | 73 | 36.5333 | 3323.774 | 0 | 1847.982 | 1425.791
29803 | Project Readiness Financing (PRF) for Punjab Provincial Projects- Punjab Intermediate Cities Improvement Investment Program (PHASE-II) | LG&CD Department | LG&CD Department | Multiple Region | 2020-11-30 | 2025-06-28 | 56 | 27.9 | 4625.52 | 1 | 2531 | 2054.519
29829 | Punjab Cities Programme- TA Component | LG&CD Department | World Bank | Multiple Region | 2019-07-01 | 2026-03-31 | 82 | 36.5333 | 3058 | 1 | 2120 | 68
29843 | Re-construction of Old P&D Building- Lahore | S&GAD | S&GAD | North Single | 2023-07-01 | 2026-06-30 | 37 | 12.1833 | 5867.61 | 0 | 5000 | 866.61
29938 | Establishment of 200 Bedded Mother & Child Hospital in District Rajanpur | Infrastructure Development Authority Punjab (IDAP) | Federal Fund- Health & Population Department | South Single | 2021-03-15 | 2024-03-14 | 37 | 26.15 | 9028.75 | 0 | 3867.03 | 5160.72
30164 | Dualization of Sialkot Pasrur Road- District Sialkot | Communication & Works Department | Communication & Works Department- Government of Punjab | North Single | 2019-09-02 | 2028-06-29 | 107 | 35.4833 | 6494.731 | 0 | 6156.628 | 297.103
30169 | Construction of Flyover at Nadirabad Phatak to Industrial Estate - Multan. | Communication & Works Department | Roads | South Single | 2020-02-04 | 2028-06-30 | 102 | 32.9 | 5377.162 | 0 | 4114.315 | 1162.847
30179 | Dualization of Lodhran Kheror Pacca- Malsi Vehari Road District Lodhran (Phase-II) Remaining 20 Km | Communication & Works Department | Communication & Works Department- Government of Punjab | South Single | 2019-09-02 | 2028-06-29 | 107 | 35.4833 | 4242.283 | 0 | 1607.819 | 2518.464
30442 | Dualization / Improvement of Multan Mattital Road (length 21 Kms) District Multan | Communication & Works Department | Communication & Works Department- Government of Punjab | South Single | 2019-09-02 | 2028-06-30 | 107 | 35.4833 | 2618.161 | 0 | 2166.296 | 397.865
32587 | Design and Construction of Net Zero Energy Building (ACEIP - DLI-8) | Energy Department | Energy Department | North Single | 2020-07-01 | 2027-06-30 | 85 | 30.4333 | 5781.95 | 0 | 2085 | 3505.146
32737 | Punjab Human Capital Investment Project (PHCIP) | Primary and Secondary Healthcare Department- Punjab Social Protection Authority- School Education Department | Planning & Development Board- Punjab | Multiple Region | 2020-04-30 | 2026-06-30 | 75 | 31.4667 | 41664 | 1 | 31811 | 167
32962 | Enhanced Air Quality Monitoring System In Punjab (DLI-2- PGDP) | Environment Protection & Climate Change Department | Environment Protection & Climate Change Department | Punjab Based | 2021-07-01 | 2025-06-30 | 49 | 24.35 | 5205.3 | 0 | 3398.5 | 1026.8
33405 | Establishment of Mother & Child Block- Teaching Hospital- DG Khan | Communication & Works Department- DG Khan Medical College | Specialized Healthcare and Medical Education Department | South Single | 2020-07-01 | 2026-06-30 | 73 | 30.4333 | 4463.757 | 0 | 1081.935 | 2381.818
33884 | Enhanced Water Quality Monitoring System In Punjab (DLI-2- PGDP) | Environment Protection & Climate Change Department | Environment Protection & Climate Change Department | Punjab Based | 2020-07-01 | 2024-06-30 | 49 | 30.4333 | 2972.72 | 0 | 1144.9 | 1197.82
34010 | Extension of Colony Protection Bund of Marala Barrage and Realignment of Tunnelwah Nullah in Sialkot District | Irrigation | Irrigation | North Single | 2020-07-01 | 2026-06-30 | 73 | 30.4333 | 3162.289 | 0 | 708 | 1854.289
34257 | Establishment of 200 Bedded Mother & Child Hospital in District Bahawalnagar | Infrastructure Development Authority Punjab (IDAP) | Federal Fund- Health & Population Department | South Single | 2021-03-01 | 2025-06-30 | 53 | 26.3833 | 6385.33 | 0 | 3375.335 | 2009.995
34384 | Construction of South Punjab Secretariat & GOR At Bahawalpur and Multan | Infrastructure Development Authority Punjab (IDAP) | S&GAD SPb | South Single | 2021-02-11 | 2025-06-30 | 53 | 26.6833 | 7407.027 | 0 | 3522.374 | 3883.653
34413 | Induction of Eco-Friendly Buses in Cities of Punjab (DLI-6 PGDP) | Punjab Transport Company (PTC)- GoPb- Transport & Masstransit Department- GoPb | Transport & Masstransit Department- GoPb | North Single | 2023-11-03 | 2026-05-31 | 31 | 10.1 | 4582.589 | 0 | 4151.78 | 215.809
34447 | Extension of District Courts Complex Multan | Communication & Works Department- Infrastructure Development Authority Punjab (IDAP) | Judiciary | South Single | 2022-02-10 | 2027-06-30 | 66 | 20.6167 | 5624.016 | 0 | 2448.452 | 3075.564
34471 | Provision of Infrastructural- Academic and Operational Facilities to the Punjab University of Technology- Rasul- M.B.Din | Communication & Works Department | Commerce & Investment | North Single | 2021-07-01 | 2026-06-29 | 61 | 24.35 | 7525.541 | 0 | 5049.411 | 2076.13
34473 | Upgradation of DHQ Hospital District Hafizabad | Health & Population Department | Federal Fund- Health & Population Department | North Single | 2021-03-24 | 2024-06-30 | 40 | 26 | 9795.184 | 0 | 6013.839 | 2781.344
35568 | Koh-E-Suleman Improvement Project (KSIP) | Planning & Development Board- Punjab | Planning & Development Board- Punjab | South Single | 2021-07-01 | 2026-06-30 | 61 | 24.35 | 5712 | 0 | 3573.033 | 168.967
35606 | Establishment of Public Financial Management Unit (PFMU)- Finance Department & Program Support Unit (PSU) Planning & Development Board under Punjab Resource Improvement and Digital Effectiveness (PRIDE)-TA Component | Finance Department- Planning & Development Board- Punjab | Planning & Development Board- Punjab | Punjab Based | 2021-07-01 | 2025-06-30 | 49 | 24.35 | 4968.6 | 1 | 253.772 | 4636.818
35995 | Construction of Sorra Dam | Irrigation | Irrigation | South Single | 2021-07-01 | 2026-06-30 | 61 | 24.35 | 8151.58 | 0 | 1392 | 6049.58
36137 | Establishment of University of Applied Engineering and Emerging Technologies (UAEET)- Sialkot | Infrastructure Development Authority Punjab (IDAP) | Higher Education Department | North Single | 2021-09-08 | 2027-06-30 | 71 | 23.2 | 17685.703 | 0 | 3169.785 | 14415.918
36262 | Punjab Rural Sustainable Water Supply and Sanitation Project | LG&CD Department | LG&CD Department | Punjab Based | 2021-07-01 | 2028-06-30 | 85 | 24.35 | 96202 | 1 | 39125 | 30705.199
36267 | Establishment of University of Gujranwala | Higher Education Department | Higher Education Department | North Single | 2023-08-22 | 2026-06-30 | 35 | 11.3167 | 5299.714 | 0 | 1335.591 | 3914.123
36391 | Establishment of Emergency and OPD Block Teaching Hospital- DG Khan | Communication & Works Department- DG Khan Medical College | Specialized Healthcare and Medical Education Department | South Single | 2021-07-01 | 2026-06-29 | 61 | 24.35 | 4035.184 | 0 | 1111.57 | 1923.614
36494 | Establishment of 200 Bedded Mother & Child Hospital at Ghalla Godam- Multan | Communication & Works Department- Nishtar Medical University & Allied Hospital- Multan | Specialized Healthcare and Medical Education Department | South Single | 2021-04-07 | 2026-06-30 | 64 | 25.7667 | 8116.778 | 0 | 2931.749 | 4685.024
37208 | Implementation of Universal Health Coverage under Health Insurance Program in Punjab | Punjab Health Initiative Management Company (PHIMC)- Specialized Healthcare and Medical Education Department | Specialized Healthcare and Medical Education Department | Punjab Based | 2021-07-01 | 2026-06-30 | 61 | 24.35 | 332845 | 0 | 200499 | 107346
37327 | Land Acquisition & Utility Shifting for Dualization of Faisalabad - Chiniot - Sargodha Road (Length =67 Km) - Under PPP Mode | Roads | Communication & Works Department | North Single | 2021-05-10 | 2026-06-30 | 63 | 25.2167 | 3494.391 | 0 | 3127.247 | 323.144
37474 | Improving Workforce Readiness in Punjab Project (Cost: FEC $100m- Local $10m) | Skill Development & Entrepreneurship Department | Skill Development & Entrepreneurship Department | Punjab Based | 2023-01-13 | 2028-12-29 | 73 | 15 | 23982 | 1 | 6510.312 | 14327.386
40989 | Umbrella PC-I for provision of land Acquisition / Compensation of structure and PST pertaining to PSDP funded schemes. | Communication & Works Department | Government of Punjab | South Single | 2021-07-01 | 2026-06-30 | 61 | 24.35 | 9816.476 | 0 | 7011.649 | 2747.827
43417 | Punjab Urban Land Systems Enhancements (PULSE) | BOR- Punjab Land Records Authority (PLRA) | World Bank | Punjab Based | 2022-07-01 | 2027-06-30 | 61 | 18.2667 | 26440.704 | 1 | 1479.67 | 14811.034
44394 | Construction of Bachelor accommodation and Judicial Rest House at Dharampura- District Lahore | Communication & Works Department | Judiciary | North Single | 2022-07-01 | 2026-06-29 | 49 | 18.2667 | 3687 | 0 | 3452.96 | 184.04
44493 | Strengthening of Punjab Tianjin University of Technology (PTUT)- Lahore | Communication & Works Department- Punjab Tianjin University of Technology (PTUT) | Industries- Commerce & Investment | North Single | 2022-07-01 | 2026-06-29 | 49 | 18.2667 | 6281.649 | 0 | 293.958 | 5707.691
45184 | Establishment of Mir Chakar Khan Rind University of Technology- Dera Ghazi Khan | Communication & Works Department- Industries- Commerce & Investment | Industries- Commerce & Investment | South Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 4639.225 | 0 | 273 | 4116.225
45331 | Punjab Resilient and Inclusive Agriculture Transformation (PRIAT) (2022-23 to 2026-27) | Agriculture Department | Agriculture Department- Government of Punjab | Punjab Based | 2022-07-01 | 2027-06-30 | 61 | 18.2667 | 54935.56 | 1 | 37250.317 | 3761.622
45369 | Construction Of Green Building for EMC- EPD and Allied New Entities Established Under PGDP (DLI-2- PGDP) | Infrastructure Development Authority Punjab (IDAP) | Environment Protection & Climate Change Department | North Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 3723.93 | 0 | 2378 | 7.33
45600 | Construction of Rawalpindi Ring Road-R3(38.3 KM) Main Carriageway (MCW) from Banth (N-5) to Thalian (M-2) | RDA | HUD&PHED | North Single | 2022-03-08 | 2026-06-29 | 52 | 20.1833 | 32997.054 | 0 | 22987.987 | 1209.067
45713 | Jinnah Institute of Cardiology- Lahore | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | North Single | 2022-03-17 | 2026-06-29 | 52 | 20.0333 | 8837.533 | 0 | 6016.076 | 0
46285 | Punjab affordable Housing Project (TA Component) | Punjab Housing and Town Planning Agency (PHATA) | HUD&PHED | Punjab Based | 2023-03-02 | 2028-06-13 | 64 | 14.2 | 3000 | 1 | 513.581 | 1906.419
46296 | Construction of Arterial Main Secondary and Distribution Network in the Areas in the Eastern Part of City (Linked with AFD Funded Extension of Water Resources in Faisalabad City Phase-II Project) | WASA Faisalabad | HUD&PHED | North Single | 2023-09-14 | 2028-06-30 | 58 | 10.9333 | 8453.607 | 0 | 1466.07 | 5987.537
46458 | Program for Provision of Missing Facilities in Newly Upgraded Colleges of Nursing in Punjab | Communication & Works Department- D.G Nursing Punjab | Specialized Healthcare and Medical Education Department | Punjab Based | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 2612.671 | 0 | 2411.792 | 0
47202 | National Health Support Program (NHSP) (TA Component) | Health & Population Department | Health & Population Department | Punjab Based | 2022-07-01 | 2026-12-31 | 55 | 18.2667 | 6382.782 | 1 | 534.236 | 5355.546
47203 | Punjab Family Planning Program (Technical Assistance Component) | Health & Population Department | Health & Population Department | Punjab Based | 2023-07-01 | 2027-06-30 | 49 | 12.1833 | 4282.35 | 1 | 1885.05 | 1045.9
47404 | Construction of Dual Carriageway from Sheikh Fazal to Chichawatni - Length-24.15 Km | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 4596.256 | 0 | 4594.256 | 0
47476 | Widening / Improvement of Manga Raiwind Road- Length 18.00 Km. | Communication & Works Department | Government of Punjab | North Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 2609.289 | 0 | 1939.946 | 589.343
47540 | Rehabilitation of Faisalabad circular road / By Pass Ring Length = 97.80 Km. | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 7064.501 | 0 | 7060.501 | 3.9
47576 | Rehabilitation of Khushab Muzaffar Garh road Km No. 70.70 to 134.80 (District boundary Khushab to Daal More) District Jhang | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 2967.815 | 0 | 2387.12 | 510.695
47593 | Rehabilitation of Akwal-Tammun-Multan Khurdh- Shah Muhammad Wali to CPEC Tarap Interchange L = 49.00 Km | Communication & Works Department | Government of Punjab | North Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 2616.399 | 0 | 2606.399 | 0
47606 | Rehabilitation of Dual Carriageway Kasur Depalpur road Length 98.95 Km District Kasur & Okara | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 6997.31 | 0 | 6996.31 | 0
47609 | Rehabilitation / Improvement of Lahore Jaranwala road Length 99.00 Km District Sheikhupura. | Roads | Roads | North Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 6995.513 | 0 | 4579.31 | 2276.203
47610 | Rehabilitation of metalled road Sahiwal to Pakpattan Length 40.00 Km- District Sahiwal | Communication & Works Department- Roads | Communication & Works Department- Roads | North Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 4223.432 | 0 | 4091.865 | 0
47845 | Rehabilitation of Shahdara - Maqboolpura - Kala Khatai - Narang Mandi Road Length=34.11 Km in Tehsil Ferozewala District Sheikhupura | Communication & Works Department | Communication & Works Department | North Single | 2022-07-01 | 2026-06-30 | 49 | 18.2667 | 3515.733 | 0 | 3473.293 | 0
49249 | Construction/ Widening / Improvement of Road from Hafizabad to Gujrat via Head Khanki along L.C.C Mian Canal- Length = 45.00 Km- District Hafizabad & Gujranwala | Roads | Roads | North Single | 2022-11-21 | 2026-06-30 | 44 | 15.8833 | 8296.554 | 0 | 3322.357 | 4877.197
52129 | Construction of New Courts Blocks at the Site of old Administration Block at Lahore High Court- Lahore | Communication & Works Department | Judiciary | North Single | 2023-05-31 | 2027-06-29 | 50 | 12.7 | 5671.377 | 0 | 2945 | 1926.377
52357 | Re-construction of Lady Willingdon Hospital- Lahore | Infrastructure Development Authority Punjab (IDAP)- King Edward Medical University | Specialized Healthcare and Medical Education Department | North Single | 2023-08-21 | 2026-06-30 | 35 | 11.3333 | 7508.45 | 0 | 4173 | 2599.45
52419 | Development of a Controlled Access Corridor Facility from Niazi Interchange to to Babu Sabu Interchange Lahore | LDA | HUD&PHED | North Single | 2023-09-08 | 2026-06-30 | 34 | 11.0333 | 11355.157 | 0 | 11354.157 | 0
52466 | Rehabilitation and Development of Qila Kohna Qasim Bagh (QKQB) for the Promotion of Tourism and Preservation of Tangible and Intangible Heritage- Multan | Walled City of Lahore Authority | LG&CD Department | South Single | 2023-11-13 | 2026-06-29 | 32 | 9.9333 | 2781.41 | 0 | 400 | 2281.409
52527 | Implementation of Flood Protection Sector Project-III (FPSP-III) | Irrigation | Irrigation | Punjab Based | 2023-07-01 | 2026-06-30 | 37 | 12.1833 | 2971 | 0 | 0 | 2970
55079 | Construction of 313 Residences for Police Officers/ Official (BS 1-20) at Lahore (Phase-I) | Communication & Works Department | Police Department | North Single | 2024-01-01 | 2026-12-31 | 37 | 9.1167 | 2941.348 | 0 | 2773.267 | 118.081
55128 | Integrated Master Planning and Development / Expansion of Data Darbar Complex- Including Traffic Management | Auqaf & Religious Affairs- Communication & Works Department- LDA | Auqaf & Religious Affairs | North Single | 2024-01-31 | 2027-06-30 | 42 | 8.6167 | 6392.8 | 0 | 355.95 | 5036.85
55613 | Getting Results Access and Delivery of Quality Education Services (GRADES) | Communication & Works Department- Programme Monitoring and Implementation Unit (PMIU-PESRP)- Punjab Curriculum and Textbook Board (PCTB)- Punjab Education Foundation (PEF)- Punjab Examination Commission (PEC)- Quaid-e-Azam Academy for Educational Development (QAED)- School Education Department | World Bank | Punjab Based | 2024-06-19 | 2029-06-21 | 61 | 6.2833 | 41671.37 | 1 | 0 | 36671.37
55616 | Rehabilitation of Multan-Vehari Road Length 93.5 Km. | Communication & Works Department | Communication & Works Department | South Single | 2024-09-01 | 2028-06-30 | 47 | 5.05 | 13000 | 0 | 2000 | 6500
55619 | Dualization of Faisalabad Chiniot Sargodha road from Kamalpur Interchange to Tehsil chowk Chiniot- District Faisalabad & Chiniot Length 24.00 Km. | Communication & Works Department | Communication & Works Department | North Single | 2024-03-01 | 2026-06-30 | 28 | 8.1167 | 7575.426 | 0 | 3000 | 2535.426
55629 | Smart Safe Cities for 19 Districts (Phase II) | Punjab Safe Cities Authority (PSCA) | Police Department | Multiple Region | 2024-07-01 | 2025-06-30 | 12 | 6.0833 | 5645.91 | 0 | 3087.196 | 12.804
55681 | Punjab Socio Economic Registry (PSER) | Bureau of Statistics Punjab- District Administration- Punjab Information Technology Board (PITB)- Punjab Social Protection Authority- Urban Unit | Planning & Development Board- Punjab | Punjab Based | 2024-07-01 | 2027-06-30 | 36 | 6.0833 | 5112.68 | 0 | 1357.272 | 1706.835
55791 | Establishment of Nawaz Sharif Institute of Cancer Treatment and Research- Lahore | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | North Single | 2024-07-01 | 2027-02-28 | 32 | 6.0833 | 52772.52 | 0 | 14250.8 | 26521.72
55881 | Developing Resilient Environment and Advancing Municipal Services (DREAMS-I) | LG&CD Department | Asian Development Bank (ADB) | Multiple Region | 2024-07-01 | 2028-06-28 | 49 | 6.0833 | 64480.713 | 1 | 5783 | 54682.712
55924 | Nawaz Sharif Institute of Cardiology- Sargodha | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | North Single | 2024-07-01 | 2026-01-31 | 19 | 6.0833 | 8568.205 | 0 | 6000 | 0
55925 | Chief Minister’s "Plant for Pakistan" Initiative | Forestry- Transport | Forestry- Government of Punjab | Punjab Based | 2024-04-01 | 2028-06-30 | 52 | 7.6 | 8000 | 0 | 1800 | 1958.566
55972 | Aquaculture: Shrimp Farming in Punjab. | Communication & Works Department- Fisheries | Forestry-WildLife-Fisheries | Multiple Region | 2024-07-01 | 2028-06-29 | 49 | 6.0833 | 5010.352 | 0 | 896.919 | 335.768
56111 | Rehabilitation of Sahiwal Arifwala road upto District Boundary- Length = 27.00 Km- in District Sahiwal. | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 5334.124 | 0 | 2708 | 1385.697
56114 | Rehabilitation / Improvement of road from Fatehjang to Pidigheb road via Dhullian Km 13 to 57.50 Length = 44.50 Tehsil Fatehjang & Pindigheb District Attock | Communication & Works Department | Communication & Works Department | North Single | 2024-09-20 | 2028-09-27 | 49 | 4.7333 | 4703.316 | 0 | 1451 | 1626.316
56116 | Rehabilitation of Talagang – Kallar Kahar – Choa Saiden Shah Road. | Communication & Works Department | Communication & Works Department | North Single | 2024-08-15 | 2028-06-30 | 47 | 5.3333 | 5163.443 | 0 | 2287 | 1438.443
56123 | Rehabilitatation of road from Bahawalnagar to Head Sulemanki Length: 75.00 Km District Bahawalnagar | Communication & Works Department | Communication & Works Department | South Single | 2024-09-02 | 2028-06-30 | 47 | 5.0333 | 6781.311 | 0 | 1688 | 2793.311
56137 | Rehabilitation of road from Shahpur and Jhal Chakian to Bhalwal via Lak Morr Length (38.40+23.00) Total Length 61.40 Km in District Sargodha | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2028-06-30 | 52 | 7.6 | 4148.028 | 0 | 3758 | 195.028
56162 | Rehabilitation of G.T road from Chan Da Qila to Aziz Cross Chowk in Gujranwala City Length 12.75 Km District Gujranwala | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2028-06-30 | 52 | 7.6 | 5729.345 | 0 | 4046 | 1441.345
56164 | Rehabilitation of Jhang Bhakkar road from Mallu More to Bharairhi Km no. 231.00 to 272.00- Length 41.00 Km- District Jhang | Roads | Roads | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 3200 | 0 | 2000.725 | 599.275
56174 | Rehabilitation of Gujrat Sargodha road Km 27.90 to 122.20 (Dual Carriageway) Length 94.30 Km District M.B.Din | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2028-06-30 | 52 | 7.6 | 9802.059 | 0 | 1270 | 4532.059
56176 | Rehabilitation of Muridke Narowal road (Section Muridke to District Boundary) Sheikhupura. | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2026-06-30 | 27 | 7.6 | 8698.858 | 0 | 2336 | 3362.858
56177 | Rehabilitation / Re-Construction of road from Narowal to Muridke (Length Km No.0.00 to 33.21 = 33.21 Km upto District Boundary) District Narowal | Communication & Works Department | Communication & Works Department | North Single | 2024-04-01 | 2028-06-30 | 52 | 7.6 | 6151.531 | 0 | 2335 | 1908.531
56186 | Rehabilitation / Improvement of Sahiwal – Arifwala - Bahawalnagar Road- (Section District Pakpattan) Length = 40.25 Km in District Pakpattan. | Communication & Works Department | Communication & Works Department | North Single | 2024-07-01 | 2027-06-30 | 36 | 6.0833 | 7648.025 | 0 | 3338 | 2243.059
56191 | Development of Urban Bus Depots & Allied Infrastructure- Faisalabad | Punjab Transport Company (PTC)- GoPb | Transport & Masstransit Department- GoPb | North Single | 2024-08-01 | 2025-06-30 | 11 | 5.5667 | 4304.509 | 0 | 0 | 3804.509
56209 | Construction of Residences for Officials (Grade 1-10) of Lahore High Court at Harbanspura- Lahore | Communication & Works Department | Judiciary | North Single | 2024-07-01 | 2027-06-30 | 36 | 6.0833 | 2672.082 | 0 | 10 | 2462.082
57298 | Concrete Lining of Irrigation Channels to Improve Water Delivery Performance and Conveyance Efficiency-III | Irrigation | Irrigation | Punjab Based | 2024-07-01 | 2028-06-06 | 48 | 6.0833 | 3995.293 | 0 | 400 | 1195.293
57384 | Chief Minister Punjab Free Solar Panel Scheme | Energy Department | Energy Department | Punjab Based | 2024-07-01 | 2025-09-30 | 15 | 6.0833 | 9975.392 | 0 | 5772.843 | 326.402
57896 | Program for Revamping of RHCs (Phase-II) | Communication & Works Department- Health & Population Department | Health & Population Department | Punjab Based | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 4288.956 | 0 | 2144.478 | 0
57897 | Program for Revamping of BHUs of North and Central Punjab (Phase-II) | Communication & Works Department- Health & Population Department | Health & Population Department | Punjab Based | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 9594.422 | 0 | 4797.211 | 0
57924 | CM Punjab Laptop Program | Punjab Information Technology Board (PITB) | Higher Education Department | Punjab Based | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 27000 | 0 | 8042 | 3958
57946 | Central Punjab Non-Formal Education Project | Literacy & Non Formal Basic Education | Literacy & Non Formal Basic Education | North Single | 2024-11-01 | 2027-10-31 | 36 | 4.0333 | 4757.198 | 0 | 911.584 | 2785.942
58083 | Chief Minister Punjab Kissan Card (2024-25 to 2025-26) | Agriculture Department | Agriculture Department | Punjab Based | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 9000 | 0 | 2700 | 0
58091 | CM Lahore Development Program- Ravi Zone-I. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2026-06-30 | 21 | 4.5667 | 7800 | 0 | 3147 | 1373
58092 | CM Lahore Development Program- Ravi Zone-II. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2026-06-30 | 21 | 4.5667 | 7000 | 0 | 3625 | 975
58093 | CM Lahore Development Program- Data Gunj Baksh Zone. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2026-12-31 | 27 | 4.5667 | 4700 | 0 | 1945 | 805
58094 | CM Lahore Development Program- Samanabad Zone. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2027-06-30 | 33 | 4.5667 | 3050 | 0 | 1432 | 468
58095 | CM Lahore Development Program- Nishter Zone-I. | WASA Lahore | HUD&PHED | North Single | 2024-09-30 | 2026-06-30 | 21 | 4.5667 | 8000 | 0 | 3476 | 1354
58096 | CM Lahore Development Program- Nishter Zone-II. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 7901 | 0 | 3915 | 1196
58098 | CM Lahore Development Program- Wahga Zone-I. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 9699.15 | 0 | 0 | 2909.15
58099 | CM Lahore Development Program- Wahga Zone-II. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 8997.478 | 0 | 1700 | 2187.478
58101 | CM Lahore Development Program- Allama Iqbal Zone. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 9600 | 0 | 0 | 2880
58102 | CM Lahore Development Program- Aziz Bhatti Zone. | WASA Lahore | HUD&PHED | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 8250 | 0 | 0 | 2475
58237 | Chief Minister’s Program for Solarization of Agricultural Tubewells in Punjab (2024-25 to 2025-26) | Energy Department | Agriculture Department | Punjab Based | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 8826.3 | 0 | 70 | 0
58266 | Apni Chhat Apna Ghar Program | Punjab Housing and Town Planning Agency (PHATA) | HUD&PHED | Punjab Based | 2024-08-12 | 2028-12-31 | 53 | 5.3833 | 10000 | 0 | 75 | 9825
58520 | Restoration/ Improvement of Jhang Shorkot Kabirwala Road from Aliabad Bypass to District Boundary Jhang- Length = 64.40 Km- District Jhang | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2027-06-30 | 36 | 6.0833 | 3647.058 | 0 | 2626.368 | 346.69
58814 | Restoration / Improvement of Shahi Road upto Bahadurpur I/C Bypass at Khanpur and R.Y Khan Sec: Channigoth-R.Y.Khan | Communication & Works Department- Roads | Communication & Works Department- Roads | South Single | 2024-09-01 | 2028-06-30 | 47 | 5.05 | 2506.874 | 0 | 2028.381 | 375.493
59027 | Reconstruction/ Rehabilitation of GT road from Quaid-e-Azam Interchange (Lahore Ring Road) to Wahga Border- District Lahore | Communication & Works Department | Government of Punjab | North Single | 2024-08-15 | 2027-06-30 | 35 | 5.3333 | 7129.21 | 0 | 2800 | 2329.21
59157 | Establishment of Enforcement Stations of PERA in Punjab (New Construction / Rehabilitation of existing government buildings) | Communication & Works Department | S&GAD | Punjab Based | 2024-07-01 | 2027-06-30 | 36 | 6.0833 | 9209.431 | 0 | 1000 | 7709.431
59195 | South Punjab Non-Formal Education Project | Literacy & Non Formal Basic Education | Literacy & Non Formal Basic Education | South Single | 2024-11-01 | 2027-10-31 | 36 | 4.0333 | 7555.287 | 0 | 1486.44 | 4529.547
59201 | North Punjab Non-Formal Education Project | Literacy & Non Formal Basic Education | Literacy & Non Formal Basic Education | North Single | 2024-11-01 | 2027-10-31 | 36 | 4.0333 | 5299.14 | 0 | 972.039 | 3225.142
59552 | Eco-Tourism at Changa Manga and Wetlands- Uchhali & Chashma | Communication & Works Department- Wildlife | Forestry-WildLife-Fisheries | Punjab Based | 2024-07-01 | 2027-06-30 | 36 | 6.0833 | 8710.57 | 0 | 0 | 2710.57
59746 | Rehabilitation / Improvement of Roads- Streets (P.C.C.)- Sewerage / Drainage and M&R of Street Lights- Allama Iqbal-II Zone- MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-29 | 24 | 6.0833 | 9522 | 0 | 100 | 582
59874 | Rehabilitation / Improvement of Roads- Streets (P.C.C.)- Sewerage / Drainage and M&R of Street Lights- Ravi Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-11-27 | 2026-06-30 | 19 | 3.6 | 8350 | 0 | 2400 | 500
59875 | Rehabilitation / Improvement of Roads- Streets (P.C.C.) and M&R of Street Lights- Data Gunj Buksh Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 3677 | 0 | 900 | 177
59877 | Rehabilitation / Improvement of Roads- Streets (P.C.C.)- Sewerage / Drainage and M&R of Street Lights- Nishtar-I Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 8000 | 0 | 3000 | 500
59878 | Rehabilitation / Improvement of Roads- Streets (P.C.C.)- Sewerage / Drainage and M&R of Street Lights- Allama Iqbal-I Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 9000 | 0 | 11.55 | 488.45
59880 | Rehabilitation / Improvement of Roads- Streets (P.C.C.)- Sewerage / Drainage and M&R of Street Lights- Shalamar Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-11-27 | 2026-06-30 | 19 | 3.6 | 2836 | 0 | 1600 | 136
59881 | Rehabilitation / Improvement of Roads- Streets (P.C.C.)- Sewerage / Drainage and M&R of Street Lights- Aziz Bhatti Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 3947 | 0 | 100 | 147
59882 | Rehabilitation / Improvement of Roads- Streets (P.C.C.)- Sewerage / Drainage and M&R of Street Lights- Wahga Zone MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 7560 | 0 | 100 | 460
59884 | Rehabilitation / Improvement of Roads- Streets (P.C.C.)- Sewerage / Drainage and M&R of Street Lights- Nishtar-II Zone- MC Lahore | LG&CD Department | LG&CD Department | North Single | 2024-07-01 | 2026-06-29 | 24 | 6.0833 | 4000 | 0 | 1500 | 300
59926 | Establishment of Garment Cities in Punjab | Communication & Works Department- Energy Department- Forestry- Wildlife & Fisheries- Punjab Industrial Estates Development & Management Company (PIEDMC)- Technical Education & Vocational Training Authority (TEVTA) | Industries- Commerce & Investment | North Single | 2024-07-01 | 2026-06-29 | 24 | 6.0833 | 3877.864 | 0 | 2524.444 | 405.475
59988 | Rehabilitation / Improvement of Pail Chowk to Uchali Road Length=55 KM District Khushab | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2028-06-30 | 49 | 6.0833 | 3091.377 | 0 | 1100 | 1841.377
60018 | Construction of Flyover at Khawaja Corporation at Adyala Road- District Rawalpindi. | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2027-06-30 | 36 | 6.0833 | 3407.306 | 0 | 2113 | 1239.306
60020 | Construction of Underpass at GPO Chowk & TM Chowk on Mall Road Including Pedestrain Underpass near AFIC- District Rawalpindi | Communication & Works Department | Government of Punjab | North Single | 2024-07-01 | 2027-06-30 | 36 | 6.0833 | 4388.286 | 0 | 4370.286 | 0
60025 | CM Punjab: Livestock Card | Livestock & Dairy Development Department | Government of Punjab | Punjab Based | 2024-07-01 | 2026-06-30 | 24 | 6.0833 | 4382.08 | 0 | 507.64 | 2845.81
64744 | Capacity Building Project for Performance Improvement of the Lahore and Faisalabad Water and Sanitation Agencies- Punjab | HUD&PHED | HUD&PHED | North Single | 2024-12-04 | 2027-06-30 | 31 | 3.4833 | 4238.85 | 1 | 0 | 3802.85
65099 | Construction of Additional Carriageway (Dehli - Multan Road) from Pull 114/16-R to Pir Murad Morr- Length=50.60KM- District Vehari | Communication & Works Department | Government of Punjab | South Single | 2024-10-31 | 2028-06-30 | 45 | 4.05 | 8499.48 | 0 | 2200 | 3299.48
65395 | Specialized Medical Equipment for Jinnah Institute of Cardiology- Lahore | Infrastructure Development Authority Punjab (IDAP) | Specialized Healthcare and Medical Education Department | North Single | 2024-12-01 | 2026-03-17 | 16 | 3.5333 | 6889.162 | 0 | 2333.6 | 0
65455 | Punjab Smog Mitigation And Response Initiative – Air Safe | Environment Protection & Climate Change Department | Environment Protection & Climate Change Department | Punjab Based | 2024-11-14 | 2026-06-30 | 20 | 3.8167 | 5381 | 0 | 2000 | 0
65564 | Revamping of Bansara Gali Zoological Garden- Murree | Forestry- Wildlife & Fisheries | Forestry-WildLife-Fisheries | North Single | 2024-07-01 | 2027-06-30 | 36 | 6.0833 | 3915.598 | 0 | 474.076 | 301.522
65819 | Construction of Additional Carriageway (Dehli-Multan Road) from babar Chowk to Drammawala Morr- Length=19.20 Km | Communication & Works Department | Communication & Works Department | South Single | 2024-12-17 | 2028-06-30 | 43 | 3.2667 | 3108 | 0 | 1000 | 0
65866 | Replacement of Old / Condemned Equipment of PFSA (Phase-II) | Punjab Forensic Science Agency (PFSA) | Home Department | North Single | 2024-12-17 | 2026-06-30 | 19 | 3.2667 | 3414.5 | 0 | 0 | 2421.499
65877 | Construction of 03 Towers for Multistorey Building for Residences of Government Officials at Chauburji Garden Estate- Multan Road- Lahore | Communication & Works Department | S&GAD | North Single | 2024-12-19 | 2026-12-19 | 24 | 3.2333 | 3125.424 | 0 | 0 | 3115.424
65920 | Construction of Administrative Tower-A at Old P&D Building site- Lahore | Infrastructure Development Authority Punjab (IDAP) | S&GAD | North Single | 2025-04-01 | 2027-06-30 | 27 | 1.5167 | 4020.401 | 0 | 2000 | 2019.401
65957 | Community Empowerment and Strengthening of Healthcare Access through Maryam Nawaz Health Clinic | Health & Population Department | Health & Population Department | Punjab Based | 2025-02-01 | 2026-06-30 | 17 | 2.5 | 9031.286 | 0 | 343.7 | 0
66061 | CM Punjab Asaan Karobar Finance | Punjab Small Industries Corporation (PSIC) | Industries- Commerce & Investment | Punjab Based | 2025-01-01 | 2032-06-30 | 91 | 3.0167 | 9500 | 0 | 550 | 7150
66062 | CM Punjab Asaan Karobar Card | Punjab Small Industries Corporation (PSIC) | Industries- Commerce & Investment | Punjab Based | 2025-01-01 | 2030-06-30 | 67 | 3.0167 | 9500 | 0 | 500 | 7000
66250 | Comprehensive Door-to-Door Socio-Economic Survey of Punjab For Establishing Punjab Socio-Economic Registry (PSER)-PC-II | Planning & Development Board- Punjab | Planning & Development Board- Punjab | Punjab Based | 2025-02-19 | 2026-06-02 | 16 | 2.2 | 7774.314 | 0 | 158 | 0
67015 | Dualization of Road from Toba Tek Singh Interchange (M-4) to Rajana Interchange (M-3)- Length=26.44 Km- District T.T.Singh | Communication & Works Department | Communication & Works Department | North Single | 2025-03-10 | 2028-06-30 | 40 | 1.8833 | 7770.948 | 0 | 2000 | 5570.948
67295 | Construction of Punjab Revenue Authority (PRA) Headquarter | Infrastructure Development Authority Punjab (IDAP)- Public Buildings | Finance Department | North Single | 2025-03-14 | 2026-06-30 | 16 | 1.8167 | 4023 | 0 | 2000 | 2022
68035 | Rehabilitation/ Reconstruction/ Widening of Road from N-5 (Ghousia Chowk) to-Lodhran — Jalalpur Road (Jindu Morr) Via DC Office & Pathanwala including Construction of Flyover at Pathanwala Railway Crossing- Length=3.00km- District Lodhran | Communication & Works Department | Roads | South Single | 2025-03-24 | 2028-06-30 | 40 | 1.65 | 2548.03 | 0 | 0 | 2442.03
69528 | Construction of Road from Kakuwal Bridge to Kuthyala Syedan via Baha-ud-Din Kot Baloach Drain including Flyover on Railway Line- District Mandi Baha-ud-Din | Communication & Works Department | Communication & Works Department | North Single | 2025-05-06 | 2028-06-30 | 38 | 0.93333 | 3134.183 | 0 | 0 | 2958.183
70258 | IPF Component for Punjab Clean Air Program (PCAP) | Punjab Resource Management & Policy Unit (PRMPU) | Planning & Development Board- Punjab | Punjab Based | 2025-05-22 | 2030-06-30 | 62 | 0.66667 | 5700.351 | 1 | 0 | 4250.351
454 | Construction of Tamman Dam | Irrigation | Irrigation | North Single | 2014-10-16 | 2025-07-30 | 131 | 65.1833 | 4232.795 | 0 | 2906.934 | 325.861
23753 | PC-1 for Remaining Land Acquisition for GTC Project | Irrigation | Irrigation | Multiple Region | 2018-07-01 | 2025-07-31 | 86 | 42.6167 | 8171.031 | 0 | 4642.195 | 3527.836
34175 | Establishment of 200 Bedded Mother & Child Hospital in District Attock | Infrastructure Development Authority Punjab (IDAP) | Federal Fund- Health & Population Department | North Single | 2021-03-15 | 2025-07-14 | 53 | 26.15 | 5320.01 | 0 | 4820.01 | 0
37225 | Institutional Strengthening of P&D Board and Capacity Building of Public Sector Employees | Planning & Development Board- Punjab- Punjab Resource Management & Policy Unit (PRMPU) | Planning & Development Board- Punjab | North Single | 2021-07-01 | 2026-06-29 | 61 | 24.35 | 2637.012 | 0 | 1177.649 | 810.724
920 | Sewerage System from Larechs Colony to Gulshan-e-Ravi- Lahore. | WASA Lahore | HUD&PHED | North Single | 2020-06-25 | 2028-06-30 | 98 | 30.5333 | 14165.06 | 1 | 231.911 | 13635.609
3288 | Establishment of 100-Bedded Mother and Child Hospital- Murree (for Conversion into General Hospital) | Infrastructure Development Authority Punjab (IDAP)- Specialized Healthcare and Medical Education Department | Health | North Single | 2017-07-01 | 2026-06-28 | 109 | 48.7 | 4157.511 | 0 | 600 | 3556.511
4593 | Storm Water Drainage System from Haji Camp to River Ravi via Laxmi Chowk- McLeod Road- Nabha Road- Chauburji and Sham Nagar- Lahore. | WASA Faisalabad | HUD&PHED | North Single | 2016-10-20 | 2027-06-30 | 130 | 52.9333 | 4066.653 | 0 | 3646.996 | 414.657
4605 | Extension of Water Resources Faisalabad City Phase II (French Funded). | WASA Faisalabad | HUD&PHED | North Single | 2021-09-20 | 2028-09-30 | 86 | 23 | 14636.928 | 1 | 4254.5 | 4276.758
11469 | Establishment of Sports Complex Shalamar Lahore (LDP). | LDA | HUD&PHED | North Single | 2017-07-01 | 2027-06-30 | 122 | 48.7 | 2562.76 | 0 | 1068.542 | 994.218