## Sheet1 (3)
Project A
No. | Variable | Description | Value | Data Source
1 | BC | Budgeted Cost | 150 | PC-I or PC-II
2 | SD | Start Date | 2012-10-10 01:12 | PC-I or PC-II
3 | CD | Finish Date | 2017-07-04 08:35 | PC-I or PC-II
4 | DD | Data Date | 2013-06-30 | PC-III
5 | AC | Actual Cost | 15 | PC-III
6 | PPE | Physical Progress Estimate % | 0.1 | (AC/BC)
No. | Calculation | Description | Value | Formuala
7 | PD | Project Duration | 1728.3075 | (CD-SD)
8 | T | % Time used | 0.15214 | (DD-SD)/(CD-SD)
9 | PV | Planned Disbursement (Back Loaded) | 0.07 | 0.65*T^2+0.35*T
10 | PV(l) | Planned Disbursement (Range-Low) | 0.02 | -0.387 *T^3+1.442* T^2-0.055*T
11 | PV(h) | Planned Disbursement (Range-High) | 0.19 | -0.794*T^3+0.632*T^2+1.162*T
12 | TL | Latest planned time to achieve EV | 0.29 | EV=-0.387 *T^3+1.442* T^2-0.055*T
13 | TE | Earliest planned time to achieve EV | 0.08 | EV=-0.794*T^3+0.632*T^2+1.162*T
| Analysis | Performance | Value | Normal Range
14 | PPE | Within normal range | 0.1 | [0.02 to 0.19]
15 | T | Within normal range | 0.15214 | [0.08 to 0.29]
Project B
No. | Variable | Description | Value | Data Source
1 | BC | Budgeted Cost | 196.818 | PC-I or PC-II
2 | SD | Start Date | 2008-07-14 | PC-I or PC-II
3 | CD | Finish Date | 2014-05-15 | PC-I or PC-II
4 | DD | Data Date | 2013-06-30 | PC-III
5 | AC | Actual Cost | 127.9317 | PC-III
6 | PPE | Physical Progress Estimate % | 0.65 | (AC/BC)
| Calculation | Description | Value | Formuala
7 | PD | Project Duration | 2131 | (CD-SD)
8 | T | % Time used | 0.85031 | (DD-SD)/(CD-SD)
9 | PV | Planned Disbursement (Back Loaded) | 0.77 | 0.65*T^2+0.35*T
10 | PV(l) | Planned Disbursement (Range-Low) | 0.76 | -0.387 *T^3+1.442* T^2-0.055*T
11 | PV(h) | Planned Disbursement (Range-High) | 0.96 | -0.794*T^3+0.632*T^2+1.162*T
12 | TL | Latest planned time to achieve EV | 0.77 | EV=-0.387 *T^3+1.442* T^2-0.055*T
13 | TE | Earliest planned time to achieve EV | 0.5 | EV=-0.794*T^3+0.632*T^2+1.162*T
| Analysis | Performance | Value | Normal Range
14 | PPE | Below normal range | 0.65 | [0.76 to 0.96]
15 | T | Beyond normal range | 0.85031 | [0.5 to 0.77]

## Sheet1
Project A
No. | Variable | Description | Value | Data Source
1 | BC | Budgeted Cost | 150 | PC-I or PC-II
2 | SD | Start Date | 2012-10-10 01:12 | PC-I or PC-II
3 | CD | Finish Date | 2017-07-04 08:35 | PC-I or PC-II
4 | DD | Assessment Date | 2013-06-30 | PC-III
5 | D | Total Disbursement | 15 | PC-III
| Calculation | Description | Value | Formuala
6 | PD | Project Duration | 1728.3075 | (CD-SD)
7 | EV | % Disbursement | 0.1 | (D/BC)
8 | T | % Time used | 0.15214 | (DD-SD)/(CD-SD)
9 | PV | Planned Disbursement (Back Loaded) | 0.07 | 0.65*T^2+0.35*T
10 | PV(l) | Planned Disbursement (Range-Low) | 0.02 | -0.387 *T^3+1.442* T^2-0.055*T
11 | PV(h) | Planned Disbursement (Range-High) | 0.19 | -0.794*T^3+0.632*T^2+1.162*T
12 | TL | Latest planned time to achieve EV | 0.29 | EV=-0.387 *T^3+1.442* T^2-0.055*T
13 | TE | Earliest planned time to achieve EV | 0.08 | EV=-0.794*T^3+0.632*T^2+1.162*T
| Analysis | Performance | Value | Normal Range
14 | EV | Within normal range | 0.1 | [0.02 to 0.19]
15 | T | Within normal range | 0.15214 | [0.08 to 0.29]
Project B
No. | Variable | Description | Value | Data Source
1 | BC | Budgeted Cost | 196.818 | PC-I or PC-II
2 | SD | Start Date | 2008-07-14 | PC-I or PC-II
3 | CD | Finish Date | 2014-05-15 | PC-I or PC-II
4 | DD | Assessment Date | 2013-06-30 | PC-III | 71.0333
5 | D | Total Disbursement | 127.9317 | PC-III
| Calculation | Description | Value | Formuala
6 | PD | Project Duration | 2131 | (CD-SD) | 2013-01-09 20:53
7 | EV | % Disbursement | 0.65 | (D/BC) | -171.13
8 | T | % Time used | 0.85031 | (DD-SD)/(CD-SD)
9 | PV | Planned Disbursement (Back Loaded) | 0.77 | 0.65*T^2+0.35*T | 149.5817
10 | PV(l) | Planned Disbursement (Range-Low) | 0.76 | -0.387 *T^3+1.442* T^2-0.055*T | 21.65
11 | PV(h) | Planned Disbursement (Range-High) | 0.96 | -0.794*T^3+0.632*T^2+1.162*T
12 | TL | Latest planned time to achieve EV | 0.77 | EV=-0.387 *T^3+1.442* T^2-0.055*T
13 | TE | Earliest planned time to achieve EV | 0.5 | EV=-0.794*T^3+0.632*T^2+1.162*T | 0.08
| Analysis | Performance | Value | Normal Range | 170.48
14 | EV | Below normal range | 0.65 | [0.76 to 0.96] | 5.6827
15 | T | Beyond normal range | 0.85031 | [0.5 to 0.77]

## Sheet2
Project Success Factor | Item | Score (1-5)
Project Management's Competence | Competent project manager
Competencies of project management team
Leadership quality of PM
Correct choice of project management methodology/tool
Rapport of PM with contractors
The project leader possessed adequate interpersonal skills
The project leader possessed adequate administrative skills
Top management's enthusiastic support to the PM and project team at site
Project Manager's Technical capability
Good communications/feedback
Clear communication channels
Skilled and suitably qualified project team
Effective monitoring & control
Organizational & managerial environment | Favorable social environment
Sufficient staff
Rapport of PM with sponsor
There was strong local ownership of the project
Fair compensation for employees
Delegation of authority
Equitable administration for personnel
Financial and Technical Control | There was a detailed budget for the project
Budget Management
Formal Procedures
Scope and nature of work was well defined in the tender
Clear organization/job descriptions
Top Management Support | Commitment of all parties to the project
Support of Project champion
Support from stakeholders
Support from senior management
Technical Tasks | Effective change management
Having relevant past experience
Past experience of project management methodology/tool
Deviations from the plan were routinely and clearly dealt with
Personnel | Training the human resources in the skills demanded by the project
Employee development (training)
Risks were addressed/assessed/managed
The detailed project plans were understood and accepted by all team members
Project Characteristics | Uniqueness of the project activities
Urgency of need
Level of complexity project
The project goals and terms could be changed if conditions made it necessary
Contractor/ consultant performance | Good performance by contractors
Good performance by consultants
Competencies of project designers

## Sheet1 (2)
No | Parameter | Description | Value | Remarks
Status Data
1 | BAC | Budget Cost | 3722000
2 | PV | Planned Value | 1982000
3 | AC | Actual Cost | 1640000
4 | EV | Earned Value | 1450000
Basic Performance Analysis
5 | FP | Financial Progress | 44%
6 | PP | Physical Progress | 39%
Schedule Analysis
7 | SV | Schedule Variance | -532000 | Behind Schedule
8 | SPI | Schedule Performance Index | 0.73 | Behind Schedule
Budget Analysis
9 | CV | Cost Variance | -190000 | Over Budget
10 | CPI | Cost Performance Index | 0.88 | Over Budget
Budget Forecast
11 | EAC1 | Estimate at Completion | 3912000 | 5% Over budget
12 | EAC2 | Estimate at Completion (Low) | 4209710 | 13% Over budget
13 | EAC3 | Estimate at Completion (High) | 5754239 | 55% Over budget
Time Forecast
14 | PD | Planned Duration | 8 | Months
15 | ED | Expected Duration | 11 | Months

## Sheet3
No | Project Name | BAC | PV | EV | AC | CV | CPI | SV | SPI | EAC | VAC | FP | PP
| 2 | 3 | 4 | 5 | 6 | 7 | 9 | 8 | 10 | 11 | 12 | 13 | 14
1 | Primary School Peshawar | 8497 | 2800 | 1700 | 2200 | -500 | 0.77 | -1100 | 0.61 | 8997 | 5.9% | 25.9% | 20%
2 | Primary School Bardan | 2159 | 1600 | 1258 | 1350 | -92 | 0.93 | -342 | 0.79 | 2251 | 4.3% | 62.5% | 58.3%
3 | Irrigation Channel | 374955 | 98000 | 56256 | 70362 | -14106 | 0.8 | -41744 | 0.57 | 389061 | 3.8% | 18.8% | 15%
4 | Basic Helath Peshawar | 16917 | 1200 | 820 | 850 | -30 | 0.96 | -380 | 0.68 | 16947 | 0.2% | 5% | 4.8%
5 | Basic Health Unit Bannu | 1780 | 1500 | 1300 | 1600 | -300 | 0.81 | -200 | 0.87 | 2080 | 16.8% | 89.9% | 73%
6 | High School Tank | 10188 | 4500 | 2500 | 2350 | 150 | 1.06 | -2000 | 0.56 | 10038 | -1.5% | 23.1% | 24.5%
7 | Road N7 section 2 | 56805 | 8200 | 6800 | 7952 | -1152 | 0.86 | -1400 | 0.83 | 57957 | 2% | 14% | 12%
8 | Road Farm to Market | 61556 | 56480 | 32520 | 43735 | -11215 | 0.74 | -23960 | 0.58 | 72771 | 18.2% | 71% | 52.8%
| Portfolio Performance | 532857 | 174280 | 103154 | 130400 | -27245 | 0.79 | -71126 | 0.59 | 560102 | 5.1% | 24.5% | 19.4%
|  | VAC: ** Values in 000's | ** Values in 000's